## Golden × Live
Activity Group | Item | System | Action | Comments | TCode | Type | Dep | Plan | NEEDED (Y/N) | DONE (Y/N) | IN CHARGE | WHO (Responsible + Backup) | Tables | STEM | UNES | IBE | IIEP | UBO | UIL | UIS | ICTP | ICBA | MGIE
Foundation
Foundation | 1 | SAP FI | Create / Copy Company Code | Base legal entity record | EC01 / OX02 | Config |  |  | Y | Done | DBS | P.Lopez | T001, T001A, T001Q | ✓ | ◐ 2/3 | ∅ | ◐ 2/3 | ∅ | ∅ | ∅ | ✓ | ◐ 2/3 | ◐ 2/3
Foundation | 2 | SAP FI | Add Group Currency | Parallel currency activation | OB22 | Config | 1 |  | Y | Done | DBS | P.Lopez | T001A | ✓ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✓ | ✗ | ✗
Foundation | 3 | SAP FI | Company code global parameters | KTOPL, PERIV, FSTVA, WAERS | OBY6 | Config | 1 |  | Y | Done | DBS | P.Lopez | T001 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓
Foundation | 4 | SAP FI | Extend GL per co code (SKB1) | Aligned STEM 2026-04-15 | FS00 | Master Data | 1 |  | Y | Done | DBS | P.Lopez | SKB1 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✗
Foundation | 5 | SAP FM | Create FM area + config | FIKRS=BUKRS | OF01 | Config | 1 |  | Y | Done | DBS | I. Konakov | FM01 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓
Foundation | 6 | SAP FM | Activate FM components | XFMCO, XFMCB, XFMCA | OFUP | Config | 5 |  | Y | Done |  | I. Konakov | FM01 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓
Foundation | 7 | SAP FM | Create commitment items | 22-26 items at UNESCO | FMCIA / FMCI | Master Data | 5 |  | Y | Todo | DBS | I. Konakov | FMCI, FMCIT | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Foundation | 8 | SAP FM | Fund types |  | FM5D | Master Data | 5 |  | Y | In Progress |  | I. Konakov | FMFUNDTYPE, V_FMFUNDTYPE | ◐ 1/2 | ◐ 1/2 | ∅ | ◐ 1/2 | ∅ | ∅ | ∅ | ◐ 1/2 | ◐ 1/2 | ◐ 1/2
Foundation | 9 | SAP FM | Create fund centers |  | FMSA | Master Data | 5 |  | Y | Todo |  |  | FMFCTR, FMFCTRT | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Foundation | 10 | SAP FI-CO | Create CO area + hierarchy | KOKRS=BUKRS per UNESCO | OKKP | Config | 1 |  | Y | Done | DBS | P.Lopez | TKA00, TKA01, TKA02, TKA07, TKA09 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓
Foundation | 11 | SAP FI-CO | CO versions + plan | Plan settings | OKEQ | Config | 10 |  | Y | Todo | DBS | P.Lopez | TKA30, TKA31, V_TKA3 | ✗ | ◐ 1/3 | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Foundation | 12 | SAP FI-CO | Create cost elements | STEM aligned 2026-04-15 | KA01 / OKTZ | Master Data | 10,4 |  | Y | In Progress | DBS | P.Lopez | CSKA, CSKB, CSKU | ◐ 1/3 | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Foundation | 13 | SAP FI-PS | PS integration (profiles) | Project profiles | OPSA / OPSB | Config | 10 | 2026-04-10 | Y | Manual | DBS | R. Rios |  | — | — | — | — | — | — | — | — | — | —
Chart of account Review
Chart of account Review | 14 | SAP FI | GL automatic account determination | GR/IR, FX, tax | OBYC / OBYA | Config | 4 |  | N |  |  |  | T030, T030K | ✗ | ◐ 1/2 | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Chart of account Review | 15 | SAP FI | Exchange rate diff accounts | Per valuation method | OBA1 | Config | 4,14 |  | N |  |  |  | T030H, T030HB | ✗ | ◐ 1/2 | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Chart of account Review | 16 | SAP FI | Retained earnings account | Per co code | OB53 | Config | 4 |  | N |  |  |  | T030 | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Banking/Payment
Banking/Payment | 17 | SAP FI | Create house banks | Country-specific | FI12 | Config | 1 |  | N |  |  |  | T012, T012D, T012T | ◐ 2/3 | ◐ 2/3 | ∅ | ◐ 2/3 | ∅ | ∅ | ∅ | ◐ 2/3 | ◐ 2/3 | ◐ 2/3
Banking/Payment | 18 | SAP FI | Bank directory entries | Country bank directory + SWIFT | FI01 | Master Data | 17 |  | N | Todo |  |  | BNKA, T012A, T012B, T012C, T018C, T018D, T018V, T028, T028B | ✗ | ◐ 6/9 | ∅ | ✗ | ∅ | ∅ | ∅ | ◐ 6/9 | ✗ | ✗
Banking/Payment | 19 | SAP FI | Bank accounts (T012K) | GL per bank account | FI12 | Config | 17 |  | N | Done |  |  | T012K | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓
Banking/Payment | 20 | SAP FI | Electronic Bank Statement | Transaction types, determination | OT83 / FF.5 | Config | 17,19 |  | Y | Todo |  |  | T028G, T028I, T028S | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Banking/Payment | 21 | SAP FI | FBZP — All company codes | Base co code payment setup | FBZP | Config | 1 |  | Y | Done |  |  | T042 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓
Banking/Payment | 22 | SAP FI | FBZP — Paying company codes | Methods + signatory | FBZP | Config | 21 |  | Y | In Progress |  |  | T042C, T042T | ◐ 1/2 | ◐ 1/2 | ∅ | ◐ 1/2 | ∅ | ∅ | ∅ | ◐ 1/2 | ◐ 1/2 | ◐ 1/2
Banking/Payment | 23 | SAP FI | Payment methods per country | Country-level | FBZP | Config | 21 |  | Y |  |  |  | T042E | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓
Banking/Payment | 24 | SAP FI | Payment methods per co code | Method limits | FBZP | Config | 22,23 |  | Y | Done |  |  | T042B | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓
Banking/Payment | 25 | SAP FI | Bank determination / ranking | Critical for F110 | FBZP | Config | 19,24 |  | Y | Todo |  |  | T042I | ✗ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✗ | ✓
Banking/Payment | 26 | SAP FI | FBZP extras (T042A/D/V/P/S/W/Y/ZA) | Full F110 variants (ICTP-style) | FBZP | Config | 19,25 |  | N | Todo |  |  | T042A, T042D, T042P, T042S, T042V, T042W, T042Y, T042ZA | ✗ | ◐ 6/8 | ∅ | ◐ 3/8 | ∅ | ∅ | ∅ | ◐ 6/8 | ✗ | ◐ 3/8
Banking/Payment | 27 | SAP FI | DMEE payment format tree | Country format | DMEE / OBPM1 | Config | 21 |  | N | Todo |  |  | TRGD | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Banking/Payment | 28 | SAP FI | OBPM4 selection variants | Never transported | OBPM4 | Config | 27 |  | N | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
Banking/Payment | 29 | SAP FI | Cash management planning groups | Per currency | SM30 | Config | 1 |  | N |  |  |  | V_T035D | ◐ 1/2 | ✓ | ∅ | ◐ 1/2 | ∅ | ∅ | ∅ | ◐ 1/2 | ◐ 1/2 | ◐ 1/2
ValSub
ValSub | 30 | SAP FI | Create substitution rule (GGB1) | Mirror MGIE 8-step | GGB1 | Config | 4 |  | Y | In progress | DBS | I. Konakov | GB90, GB92, GB921, GB922, GGB1 | ◐ 3/5 | ◐ 3/5 | ◐ 1/5 | ◐ 3/5 | ◐ 1/5 | ◐ 1/5 | ◐ 1/5 | ◐ 3/5 | ◐ 3/5 | ◐ 3/5
ValSub | 31 | SAP FI | Assign substitution (OBBH) | T001D-family or OBBH table | OBBH | Config | 30 |  | Y | Done | DBS | I. Konakov |  | — | — | — | — | — | — | — | — | — | —
ValSub | 32 | SAP FI | Create validation rule (GGB0) — opt | Optional | GGB0 | Config | 4 |  | N |  |  |  | GB93, GGB0 | ✗ | ◐ 1/2 | ∅ | ◐ 1/2 | ◐ 1/2 | ◐ 1/2 | ◐ 1/2 | ◐ 1/2 | ✗ | ✗
ValSub | 33 | SAP FI | Assign validation (OB28) — opt | T001D row | OB28 | Config | 32 |  | N |  |  |  | T001D | ✗ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✗ | ✗
ValSub | 34 | SAP FI | ** RGUGBR00 regenerate ** | MANDATORY per env | SE38 RGUGBR00 | Activate | 30,31 |  | Y | Manual | DBS | I. Konakov |  | — | — | — | — | — | — | — | — | — | —
ValSub | 35 | SAP FI | YRGGBS00 ABAP exit per-BUKRS branch | Source code custom | SE38 | Dev | 30 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
Review Tolerances Group
Tolerances | 36 | SAP FI | Tolerance groups (FI) | Employee + posting | OBA4 / OBA0 | Config | 1 |  | Y | In Progress |  |  | T043G, T043GT, T043S, T043ST, T043T | ◐ 2/5 | ◐ 2/5 | ∅ | ◐ 2/5 | ∅ | ∅ | ∅ | ◐ 2/5 | ◐ 2/5 | ◐ 2/5
Tolerances | 37 | SAP FI | Assign users to tolerance groups | Per user, per env | OB57 | Config | 36 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
Tolerances | 38 | SAP MM | MM/IV tolerances | Invoice verification | OMR6 | Config | 1 |  | Y | In Progress |  |  | T169B, T169G, T169P, T169R, T169V | ◐ 3/5 | ✓ | ∅ | ◐ 3/5 | ∅ | ∅ | ∅ | ✓ | ◐ 3/5 | ◐ 3/5
Tax
Tax | 39 | SAP FI | Create tax codes per country | NEVER copy | FTXP | Config | 1 |  | Y | Todo |  |  | T007A, T007V, T683 | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Tax | 40 | SAP FI | Assign tax procedure to country | Country → procedure | OBBG | Config | 39 |  | Y | Todo |  |  | T005 | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Tax | 41 | SAP FI | Tax GL account determination | Per tax code | OBCN | Config | 39,4 |  | Y | Todo |  |  | T030K | ✗ | ✓ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Tax | 42 | SAP FI | Withholding tax (optional) | Country dependent | OBWP / OBWQ | Config | 39 |  | Y | Todo |  |  | T059Z | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Dunning
Dunning | 43 | SAP FI-AR | Dunning procedure | Per co code | FBMP / OB96 | Config | 1 |  | Y | In Progress |  |  | T047, T047E | ◐ 1/2 | ✗ | ∅ | ◐ 1/2 | ∅ | ∅ | ∅ | ◐ 1/2 | ◐ 1/2 | ◐ 1/2
Asset Accounting
Asset Accounting | 44 | SAP FI-AA | Chart of depreciation assignment |  | OAOB | Config | 1 |  | Y | In Progress |  |  | T093C, T093CE, T093C_RSL | ◐ 1/3 | ◐ 1/3 | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ◐ 1/3 | ◐ 1/3
Asset Accounting | 45 | SAP FI-AA | Asset class → GL determination |  | AO90 | Config | 4,44 |  | Y | In Progress |  |  | T093, T093A, T093B, T093B_RSL | ◐ 1/4 | ◐ 3/4 | ∅ | ◐ 2/4 | ∅ | ∅ | ∅ | ✓ | ◐ 1/4 | ◐ 1/4
Asset Accounting | 46 | SAP FI-AA | Depreciation keys + useful lives | Country tax | AFAMS | Config | 44 |  | Y | Todo |  |  | T093S, T093T, T093Y, T096 | ✗ | ◐ 2/4 | ∅ | ◐ 1/4 | ∅ | ∅ | ∅ | ◐ 2/4 | ✗ | ✗
Asset Accounting | 47 | SAP FI-AA | Asset transfer date | Legacy asset go-live | OAAQ | Config | 44 |  | Y | Done |  |  | T093D | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓
Controlling
Controlling | 48 | SAP FI-CO | Create main cost centers | Initial hierarchy | KS01 | Master Data | 10 |  | Y | Todo |  |  | CSKS, CSKT | ✗ | ◐ 1/2 | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Controlling | 49 | SAP FI-CO | Default cost center per GL | FINB | OKB9 | Config | 48,4 |  | Y | Todo |  |  | FINB_TR_DERIVATION | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Controlling | 50 | SAP FI-CO | CO allocation cycles | Optional | KSV5 / KSU5 | Config | 48 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
FM
FM | 51 | SAP FM | Create funds |  | FM5I | Master Data | 5,8 |  | Y | Todo |  |  | FMFINT | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
FM | 52 | SAP FM | FM derivation strategy | GL→CI bridge | FMDERIVE | Config | 7 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
FM | 53 | SAP FM | AVC activation | Budget control | FMBB / FM5T | Config | 9,51 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
FM | 54 | SAP FM | Carry-forward + reassignment (FMCFC) | ICTP-pattern full carry-forward | FMBN / 2KEC | Config | 51 |  | Y | In Progress |  |  | FMCFC0, FMCFC1, FMCFC2, FMIUR, FMREAS_STRATS, FMZUCO | ◐ 1/6 | ✓ | ∅ | ◐ 5/6 | ∅ | ∅ | ∅ | ◐ 5/6 | ✓ | ◐ 5/6
Consolidation
Consolidation | 55 | SAP FI-LC | Consolidation unit assignment |  | OC13 | Config | 1 |  | Y | Done |  |  | T882 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓
Cash Journal
Cash Journal | 56 | SAP FI | Cash journal setup | Optional petty cash | FBCJC0 | Config | 4 |  | Y | Todo |  |  | TCJ_CJ_NAMES, TCJ_C_JOURNALS, TCJ_PRINT, TCJ_TRANSACTIONS, TCJ_TRANS_NAMES | ✗ | ◐ 4/5 | ∅ | ◐ 4/5 | ∅ | ∅ | ∅ | ◐ 4/5 | ◐ 4/5 | ◐ 4/5
Cross-Company
Cross-Company | 57 | SAP FI | Cross-company clearing pairs | F01U pairs bilateral | OBYA | Config | 4 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
MM
MM | 58 | SAP MM | Plant creation + assignment | Only if procures | OX10 / OX18 | Config | 1 |  | Y | Todo |  |  | T001K, T001W | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
MM | 59 | SAP MM | Purchasing organization |  | OX17 | Config | 58 |  | Y | In Progress |  |  | T024, T024E, T024W | ◐ 1/3 | ◐ 1/3 | ∅ | ◐ 1/3 | ∅ | ∅ | ∅ | ◐ 1/3 | ◐ 1/3 | ◐ 1/3
MM | 60 | SAP MM | MM Account assignment + GBB/WRX | UNESCO-custom keys | OME9 / OBYC | Config | 58,4 |  | Y | Todo |  |  | UNESGBB, UNESWRX | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
MM | 61 | SAP MM | Release strategy | PO approval workflow | OMGQ | Config | 58,59 |  | Y | Todo |  |  | T16F, T16FG_2, T16FG_3 | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Inventory & Procurement
Inventory | 62 | Inventory Management | Inventory Management setup | To conclude, need Org. STEM |  | Setup | 1 |  | Yes | In Progress | DBS | R. Rios
HR/Travel
HCM / HR / Travel | 63 | SAP HR | Personnel area + subarea | Country + subarea | OOMO | Config | 1 |  | Y | Todo |  |  | T500P, T542A | ✗ | ◐ 1/2 | ∅ | ◐ 1/2 | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
HCM / HR / Travel | 64 | Org Structure | Define Institute Org Structure | Create new or transfer HR Workflow |  | Setup | 1 | 2026-04-15 | Y |  | HRM
HCM / HR / Travel | 65 | PA | Personal Administration — transfer staff to new co code | *** MUST BE DONE BEFORE 17/04 *** |  | Master Data | 1 |  | Y |  | HRM
HCM / HR / Travel | 66 | SAP HCM | HCM customizing tables (T778A/V/U, T527O, T9SCT) + Infotypes 1000/1001/1081/00001 | Business should provide institute org structure |  | Config | 1 | 2026-04-03 | Yes |  | DBS | A. Sefiani | T778A,T778V,T778U,T527O,T9SCT
HCM / HR / Travel | 67 | SAP HR-TV | TV customizing | Travel personnel link | PR05 | Config | 63 |  | Y | Todo |  |  | TPIR2, TPIR2T | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
HCM / HR / Travel | 68 | SAP-ROLE HR | Clone Y_*_HR roles + assign + block old | Explore copy from MGIE roles. 5 days | PFCG | Role | 4 | 2026-04-10 | Yes |  | DBS | P. Ikouna
HCM / HR / Travel | 69 | HR-AP | Initial Vendor Creation (HR review) | Business activity. Automatic HR review |  | Master Data | 1 |  | Y |  | DBS FIN
HCM / HR / Travel | 70 | Core HR+ | Core HR setup | Not a blocker for Financial Execution |  | Setup | 1 |  | Yes |  | DBS | Adil, Laia
Identity & Access
Identity & Access | 71 | Active Directory | Create new accounts + AD groups | UNESDIR may auto-create following naming convention |  | Setup | 1 |  | Yes |  | DBS/OSM/NSO | C. Souvanthong
Identity & Access | 72 | Role Mgmt | Create Places |  |  | Config | 1 |  | Yes |  | DBS | Dimitri
Identity & Access | 73 | Role Mgmt | Create users with appropriate roles under new places | Verify Payment approval invoice roles |  | Config | 1 |  | Yes |  | FIN
Auth Roles
Auth Roles | 74 | SAP ROLE | Clone Y_*_* roles (~48) | Y_XXXX_* pattern | PFCG / SUPC | Role | 4 | 2026-04-10 | Y | Todo | DBS | P. Ikouna | AGR_TIMEB, SPERS_OBJ, USR12, USR13, UST12 | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Auth Roles | 75 | SAP ROLE | Assign roles to users | Per env | SU01 / SU10 | Role | 74 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
Auth Roles | 76 | SAP ROLE | Update F_BKPF_BUK values | Multi-BUKRS roles | PFCG | Role | 74 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
Master Data
Master Data | 77 | SAP FI-AP | Extend vendors to co code | LFB1 per BUKRS | FK01 / XK01 | Master Data | 1,4 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
Master Data | 78 | SAP FI-AR | Extend customers to co code | KNB1 per BUKRS | FD01 / XD01 | Master Data | 1,4 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
Activation
Activation | 79 | SAP FI | Open posting periods | Not transported — per env | OB52 | Config | 1 |  | Y | Todo | FIN/FAS/FRA | J.La | T001B | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Activation | 80 | SAP FI | Document + object number ranges | Per env | FBN1 / OBH2 | Config | 1 |  | Y | Todo | DBS | P.Lopez | NRIV | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗
Activation | 81 | SAP FI-AA | Open AA period | Per fiscal year | OAAQ | Config | 47 |  | Y | Done |  |  | T093D | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓
DUO Applications
DUO Applications | 82 | MOUV | Synchronize SAP Master Data | 1 day |  | Sync | 1 |  | Yes |  |  | S. Dartigolle, R.Rios
DUO Applications | 83 | CMT | Synchronize SAP Master Data | 1 day |  | Sync | 1 |  | Yes |  | DBS | D. Andros
DUO Applications | 84 | HR Workflow | Add new Sector |  |  | Config | 1 |  | No |  | DBS | Naila
DUO Applications | 85 | TULIP | Add new Sector |  |  | Config | 1 |  | No |  | DBS | Naila
DUO Applications | 86 | PROSPER | BFM impact actions |  |  | Config | 1 |  | No |  | DBS | Naila
DUO Applications | 87 | INFOSERV | In UNESDIR, modify Cost Center associated to Sector/Service | To be confirmed |  | Config | 1 |  | TBD |  | DBS/IOP/TSU | Naila / Alessandra
DUO Applications | 88 | REC | Update & review Application Role name + republish web app |  |  | Config | 1 |  | No |  | DBS | S. Dartigolle
Testing
Testing | 89 | SAP FI | Test FI posting | FM + substitution check | FB50 | Test | all |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
Testing | 90 | SAP FI | Test F110 payment | Bank ranking check | F110 | Test | 25,26 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
Testing | 91 | SAP FI | Test EBS import | MT940 format | FF.5 | Test | 20 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
Testing | 92 | SAP FM | Test budget + commitment | AVC verify | FMX1 / FMBB | Test | 7,9,51,52,53 |  | Y | Manual |  |  |  | — | — | — | — | — | — | — | — | — | —
Master Data Conversion
Master Data Conversion | 93 | Balance Conversion | Balance conversion (existing movements) | Business Activity. If institute has historical movements, decide migration approach |  | Conversion | 1 |  | Y
Master Data Conversion | 94 | AP/AR | Open items AP/AR migration | Business Activity. Convert open AP/AR items |  | Conversion | 1,4 |  | Y
PPM Success Factor
Planning | 95 | Core Planner | Set up Core Planner | Once done, proceed with items 21,22 if needed |  | Config | 1 |  | Yes |  | DBS | A. Mercea
Planning | 96 | Core Manager | Set up Core Manager |  |  | Config | 1 |  | No |  | DBS | A. Mercea
Communications & Documents
Comms | 97 | COUR(R)IER | Set exceptions to separate divisions for re-invoicing |  |  | Config | 1 |  | Yes |  | DBS | C.Michiote
Comms | 98 | UNTERM | Update Terminology database | Check if Reference is updated |  | Config | 1 |  | Yes |  | CLD/T
Comms | 99 | Smart | Configure Institute options |  |  | Config | 1 |  | Yes |  | DBS | Narmin
Comms | 100 | SHAREPOINT | Rename SharePoint group or create new |  |  | Config | 1 |  | Yes |  | DBS | C.Michiote
Comms | 101 | UNESDOC | Check that replication job takes new name into account | For FO/institute |  | Config | 1 |  | No |  | DBS | ?
Comms | 102 | WATCHDOC | Implement specific groups for re-invoicing |  |  | Config | 1 |  | Yes |  | DBS | R. Lévy
Comms | 103 | OURDRIVE | Implement the new Model Filing Plan |  |  | Config | 1 |  | Yes |  | DBS | Imad