## Golden × Live
Activity Group | Item | System | Action | TCode | Type | Dep | Tables | STEM | UNES | IBE | IIEP | UBO | UIL | UIS | ICTP | ICBA | MGIE | Comments | Plan | NEEDED (Y/N) | DONE (Y/N) | IN CHARGE | WHO (Responsible + Backup)
Foundation
Foundation | 1 | SAP FI | Create / Copy Company Code | EC01 / OX02 | Config |  | T001, T001A, T001Q | ✓ | ◐ 2/3 | ∅ | ◐ 2/3 | ∅ | ∅ | ∅ | ✓ | ◐ 2/3 | ◐ 2/3 | Base legal entity record |  | Y | Done | DBS | P.Lopez
Foundation | 2 | SAP FI | Add Group Currency | OB22 | Config | 1 | T001A | ✓ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✓ | ✗ | ✗ | Parallel currency activation |  | Y | Done | DBS | P.Lopez
Foundation | 3 | SAP FI | Company code global parameters | OBY6 | Config | 1 | T001 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓ | KTOPL, PERIV, FSTVA, WAERS |  | Y | Done | DBS | P.Lopez
Foundation | 4 | SAP FI | Extend GL per co code (SKB1) | FS00 | Master Data | 1 | SKB1 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✗ | Aligned STEM 2026-04-15 |  | Y | Done | DBS | P.Lopez
Foundation | 5 | SAP FM | Create FM area + config | OF01 | Config | 1 | FM01 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓ | FIKRS=BUKRS |  | Y | Done | DBS | I. Konakov
Foundation | 6 | SAP FM | Fund types | FM5D | Config | 5 | FMFUNDTYPE, V_FMFUNDTYPE | ◐ 1/2 | ◐ 1/2 | ∅ | ◐ 1/2 | ∅ | ∅ | ∅ | ◐ 1/2 | ◐ 1/2 | ◐ 1/2 |  |  | Y | In Progress |  | I. Konakov
Foundation | 7 | SAP FM | Activate FM components | OFUP | Config | 5 | FM01 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓ | XFMCO, XFMCB, XFMCA |  | Y | Done |  | I. Konakov
Foundation | 8 | SAP FM | Create commitment items | FMCIA / FMCI | Master Data | 5 | FMCI, FMCIT | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | 22-26 items at UNESCO |  | Y | Todo | DBS | I. Konakov
Foundation | 9 | SAP FI-CO | Create CO area + hierarchy | OKKP | Config | 1 | TKA00, TKA01, TKA02, TKA07, TKA09 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓ | KOKRS=BUKRS per UNESCO |  | Y | Done | DBS | P.Lopez
Foundation | 10 | SAP FI-CO | CO versions + plan | OKEQ | Config | 9 | TKA30, TKA31, V_TKA3 | ✗ | ◐ 1/3 | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Plan settings |  | Y | Todo | DBS | P.Lopez
Foundation | 11 | SAP FI-CO | Create cost elements | KA01 / OKTZ | Master Data | 9,4 | CSKA, CSKB, CSKU | ◐ 1/3 | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | STEM aligned 2026-04-15 |  | Y | In Progress | DBS | P.Lopez
Foundation | 12 | SAP FI-PS | PS integration (profiles) | OPSA / OPSB | Config | 9 |  | — | — | — | — | — | — | — | — | — | — | Project profiles | 2026-04-10 | Y | Manual | DBS | R. Rios
GL Accounts
GL Accounts | 13 | SAP FI | GL automatic account determination | OBYC / OBYA | Config | 4 | T030, T030K | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CHART-LEVEL (KTOPL=UNES) — inherited by all institutes. Only needed if creating NEW GL accounts not in UNES chart. GR/IR, FX, tax |  | Y | Inherited
GL Accounts | 14 | SAP FI | Exchange rate diff accounts | OBA1 | Config | 4,13 | T030H, T030HB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CHART-LEVEL (KTOPL=UNES) — inherited by all institutes. Only needed if creating NEW GL accounts not in UNES chart. Per valuation method |  | Y | Inherited
GL Accounts | 15 | SAP FI | Retained earnings account | OB53 | Config | 4 | T030 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CHART-LEVEL (KTOPL=UNES) — inherited by all institutes. Only needed if creating NEW GL accounts not in UNES chart. Per co code |  | Y | Inherited
Banking/Payment
Banking/Payment | 16 | SAP FI | Create house banks | FI12 | Config | 1 | T012, T012D, T012T | ◐ 2/3 | ◐ 2/3 | ∅ | ◐ 2/3 | ∅ | ∅ | ∅ | ◐ 2/3 | ◐ 2/3 | ◐ 2/3 | Country-specific |  | Y | In Progress
Banking/Payment | 17 | SAP FI | Bank directory entries | FI01 | Master Data | 16 | BNKA, T012A, T012B, T012C, T018C, T018D, T018V, T028, T028B | ✗ | ◐ 6/9 | ∅ | ✗ | ∅ | ∅ | ∅ | ◐ 6/9 | ✗ | ✗ | Country bank directory + SWIFT |  | Y | Todo
Banking/Payment | 18 | SAP FI | Bank accounts (T012K) | FI12 | Config | 16 | T012K | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓ | GL per bank account |  | Y | Done
Banking/Payment | 19 | SAP FI | Electronic Bank Statement | OT83 / FF.5 | Config | 16,18 | T028G, T028I, T028S | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Transaction types, determination |  | Y | Todo
Banking/Payment | 20 | SAP FI | FBZP — All company codes | FBZP | Config | 1 | T042 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓ | Base co code payment setup |  | Y | Done
Banking/Payment | 21 | SAP FI | FBZP — Paying company codes | FBZP | Config | 20 | T042C, T042T | ◐ 1/2 | ◐ 1/2 | ∅ | ◐ 1/2 | ∅ | ∅ | ∅ | ◐ 1/2 | ◐ 1/2 | ◐ 1/2 | Methods + signatory |  | Y | In Progress
Banking/Payment | 22 | SAP FI | Payment methods per country | FBZP | Config | 20 | T042E | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓ | Country-level |  | Y | Done
Banking/Payment | 23 | SAP FI | Payment methods per co code | FBZP | Config | 21,22 | T042B | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓ | Method limits |  | Y | Done
Banking/Payment | 24 | SAP FI | Bank determination / ranking | FBZP | Config | 18,23 | T042I | ✗ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✗ | ✓ | Critical for F110 |  | Y | Todo
Banking/Payment | 25 | SAP FI | FBZP extras (T042A/D/V/P/S/W/Y/ZA) | FBZP | Config | 18,24 | T042A, T042D, T042P, T042S, T042V, T042W, T042Y, T042ZA | ✗ | ◐ 6/8 | ∅ | ◐ 3/8 | ∅ | ∅ | ∅ | ◐ 6/8 | ✗ | ◐ 3/8 | Full F110 variants (ICTP-style) |  | Y | Todo
Banking/Payment | 26 | SAP FI | DMEE payment format tree | DMEE / OBPM1 | Config | 20 | TRGD | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Country format |  | Y | Todo
Banking/Payment | 27 | SAP FI | OBPM4 selection variants | OBPM4 | Config | 26 |  | — | — | — | — | — | — | — | — | — | — | Never transported |  | Y | Manual
Banking/Payment | 28 | SAP FI | Cash management planning groups | OT42 | Config | 1 | T035D, T035U | ◐ 1/2 | ✓ | ∅ | ◐ 1/2 | ∅ | ∅ | ∅ | ◐ 1/2 | ◐ 1/2 | ◐ 1/2 | Per currency |  | Y | In Progress
ValSub
ValSub | 29 | SAP FI | Create substitution rule (GGB1) | GGB1 | Config | 4 | GB90, GB92, GB921, GB922, GGB1 | ◐ 3/5 | ◐ 3/5 | ◐ 1/5 | ◐ 3/5 | ◐ 1/5 | ◐ 1/5 | ◐ 1/5 | ◐ 3/5 | ◐ 3/5 | ◐ 3/5 | Mirror MGIE 8-step |  | Y | In Progress | DBS | I. Konakov
ValSub | 30 | SAP FI | Assign substitution (OBBH) | OBBH | Config | 29 |  | — | — | — | — | — | — | — | — | — | — | T001D-family or OBBH table |  | Y | Manual | DBS | I. Konakov
ValSub | 31 | SAP FI | Create validation rule (GGB0) — opt | GGB0 | Config | 4 | GB93, GGB0 | ✗ | ◐ 1/2 | ∅ | ◐ 1/2 | ◐ 1/2 | ◐ 1/2 | ◐ 1/2 | ◐ 1/2 | ✗ | ✗ | Optional |  | Y | Todo
ValSub | 32 | SAP FI | Assign validation (OB28) — opt | OB28 | Config | 31 | T001D | ✗ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✗ | ✗ | T001D row |  | Y | Todo
ValSub | 33 | SAP FI | ** RGUGBR00 regenerate ** | SE38 RGUGBR00 | Activate | 29,30 |  | — | — | — | — | — | — | — | — | — | — | MANDATORY per env |  | Y | Manual | DBS | I. Konakov
ValSub | 34 | SAP FI | YRGGBS00 ABAP exit per-BUKRS branch | SE38 | Dev | 29 |  | — | — | — | — | — | — | — | — | — | — | Source code custom |  | Y | Manual
Tolerances
Tolerances | 35 | SAP FI | Tolerance groups (FI) | OBA4 / OBA0 | Config | 1 | T043G, T043GT, T043S, T043ST, T043T | ◐ 2/5 | ◐ 2/5 | ∅ | ◐ 2/5 | ∅ | ∅ | ∅ | ◐ 2/5 | ◐ 2/5 | ◐ 2/5 | Employee + posting |  | Y | In Progress
Tolerances | 36 | SAP FI | Assign users to tolerance groups | OB57 | Config | 35 |  | — | — | — | — | — | — | — | — | — | — | Per user, per env |  | Y | Manual
Tolerances | 37 | SAP MM | MM/IV tolerances | OMR6 | Config | 1 | T169B, T169G, T169P, T169R, T169V | ◐ 3/5 | ✓ | ∅ | ◐ 3/5 | ∅ | ∅ | ∅ | ✓ | ◐ 3/5 | ◐ 3/5 | Invoice verification |  | Y | In Progress
Tax
Tax | 38 | SAP FI | Create tax codes per country | FTXP | Config | 1 | T007A, T007V, T683 | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | NEVER copy |  | Y | Todo
Tax | 39 | SAP FI | Assign tax procedure to country | OBBG | Config | 38 | T005 | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Country → procedure |  | Y | Todo
Tax | 40 | SAP FI | Tax GL account determination | OBCN | Config | 38,4 | T030K | ✗ | ✓ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Per tax code |  | Y | Todo
Tax | 41 | SAP FI | Withholding tax (optional) | OBWP / OBWQ | Config | 38 | T059Z | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Country dependent |  | Y | Todo
Dunning
Dunning | 42 | SAP FI-AR | Dunning procedure | FBMP / OB96 | Config | 1 | T047, T047E | ◐ 1/2 | ✗ | ∅ | ◐ 1/2 | ∅ | ∅ | ∅ | ◐ 1/2 | ◐ 1/2 | ◐ 1/2 | Per co code |  | Y | In Progress
Asset Accounting
Asset Accounting | 43 | SAP FI-AA | Chart of depreciation assignment | OAOB | Config | 1 | T093C, T093CE, T093C_RSL | ◐ 1/3 | ◐ 1/3 | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ◐ 1/3 | ◐ 1/3 |  |  | Y | In Progress
Asset Accounting | 44 | SAP FI-AA | Asset class → GL determination | AO90 | Config | 4,43 | T093, T093A, T093B, T093B_RSL | ◐ 1/4 | ◐ 3/4 | ∅ | ◐ 2/4 | ∅ | ∅ | ∅ | ✓ | ◐ 1/4 | ◐ 1/4 |  |  | Y | In Progress
Asset Accounting | 45 | SAP FI-AA | Depreciation keys + useful lives | AFAMS | Config | 43 | T093S, T093T, T093Y, T096 | ✗ | ◐ 2/4 | ∅ | ◐ 1/4 | ∅ | ∅ | ∅ | ◐ 2/4 | ✗ | ✗ | Country tax |  | Y | Todo
Asset Accounting | 46 | SAP FI-AA | Asset transfer date | OAAQ | Config | 43 | T093D | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓ | Legacy asset go-live |  | Y | Done
Controlling
Controlling | 47 | SAP FI-CO | Create main cost centers | KS01 | Master Data | 9 | CSKS, CSKT | ✗ | ◐ 1/2 | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Initial hierarchy |  | Y | Todo
Controlling | 48 | SAP FI-CO | Default cost center per GL | OKB9 | Config | 47,4 | FINB_TR_DERIVATION | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | FINB |  | Y | Todo
Controlling | 49 | SAP FI-CO | CO allocation cycles | KSV5 / KSU5 | Config | 47 |  | — | — | — | — | — | — | — | — | — | — | Optional |  | Y | Manual
FM
FM | 50 | SAP FM | Create fund centers | FMSA | Master Data | 5 | FMFCTR, FMFCTRT | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ |  |  | Y | Todo
FM | 51 | SAP FM | Create funds | FM5I | Master Data | 5,6 | FMFINT | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ |  |  | Y | Todo
FM | 52 | SAP FM | FM derivation strategy | FMDERIVE | Config | 8 |  | — | — | — | — | — | — | — | — | — | — | GL→CI bridge |  | Y | Manual
FM | 53 | SAP FM | AVC activation | FMBB / FM5T | Config | 50,51 |  | — | — | — | — | — | — | — | — | — | — | Budget control |  | Y | Manual
FM | 54 | SAP FM | Carry-forward + reassignment (FMCFC) | FMBN / 2KEC | Config | 51 | FMCFC0, FMCFC1, FMCFC2, FMIUR, FMREAS_STRATS, FMZUCO | ◐ 1/6 | ✓ | ∅ | ◐ 5/6 | ∅ | ∅ | ∅ | ◐ 5/6 | ✓ | ◐ 5/6 | ICTP-pattern full carry-forward |  | Y | In Progress
Consolidation
Consolidation | 55 | SAP FI-LC | Consolidation unit assignment | OC13 | Config | 1 | T882 | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓ |  |  | Y | Done
Cash Journal
Cash Journal | 56 | SAP FI | Cash journal setup | FBCJC0 | Config | 4 | TCJ_CJ_NAMES, TCJ_C_JOURNALS, TCJ_PRINT, TCJ_TRANSACTIONS, TCJ_TRANS_NAMES | ✗ | ◐ 4/5 | ∅ | ◐ 4/5 | ∅ | ∅ | ∅ | ◐ 4/5 | ◐ 4/5 | ◐ 4/5 | Optional petty cash |  | Y | Todo
Cross-Company
Cross-Company | 57 | SAP FI | Cross-company clearing pairs | OBYA | Config | 4 |  | — | — | — | — | — | — | — | — | — | — | F01U pairs bilateral |  | Y | Manual
MM
MM | 60 | SAP MM | Plant creation + assignment | OX10 / OX18 | Config | 1 | T001K, T001W | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Only if procures |  | Y | Todo
MM | 61 | SAP MM | Purchasing organization | OX17 | Config | 60 | T024, T024E, T024W | ◐ 1/3 | ◐ 1/3 | ∅ | ◐ 1/3 | ∅ | ∅ | ∅ | ◐ 1/3 | ◐ 1/3 | ◐ 1/3 |  |  | Y | In Progress
MM | 62 | SAP MM | MM Account assignment + GBB/WRX | OME9 / OBYC | Config | 60,4 | UNESGBB, UNESWRX | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | UNESCO-custom keys |  | Y | Todo
MM | 63 | SAP MM | Release strategy | OMGQ | Config | 60,61 | T16F, T16FG_2, T16FG_3 | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | PO approval workflow |  | Y | Todo
Inventory & Procurement
Inventory | 97 | Inventory Management | Inventory Management setup |  | Setup | 1 | [11 empty] | To conclude, need Org. STEM |  | Yes | In Progress | DBS | R. Rios
HR/Travel
HR/Travel | 58 | SAP HR | Personnel area + subarea | OOMO | Config | 1 | T500P, T542A | ✗ | ◐ 1/2 | ∅ | ◐ 1/2 | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Country + subarea |  | Y | Todo
HR/Travel | 59 | SAP HR-TV | Travel integration | PR05 | Config | 58 | TPIR2, TPIR2T | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Travel personnel link |  | Y | Todo
HCM / HR / Travel
HCM / HR / Travel | 80 | SAP HCM | HCM customizing tables (T778A/V/U, T527O, T9SCT) + Infotypes 1000/1001/1081/00001 |  | Config | 1 | T778A,T778V,T778U,T527O,T9SCT | [10 empty] | Business should provide institute org structure | 2026-04-03 | Yes |  | DBS | A. Sefiani
HCM / HR / Travel | 81 | SAP TV | TV customizing |  | Config | 1 | [11 empty] | 1 day | 2026-04-03 | Y |  | DBS | Laia
HCM / HR / Travel | 82 | SAP-ROLE HR | Clone Y_*_HR roles + assign + block old | PFCG | Role | 4 | [11 empty] | Explore copy from MGIE roles. 5 days | 2026-04-10 | Yes |  | DBS | P. Ikouna
HCM / HR / Travel | 83 | Org Structure | Define Institute Org Structure |  | Setup | 1 | [11 empty] | Create new or transfer HR Workflow | 2026-04-15 | Y |  | HRM
HCM / HR / Travel | 84 | PA | Personal Administration — transfer staff to new co code |  | Master Data | 1 | [11 empty] | *** MUST BE DONE BEFORE 17/04 *** |  | Y |  | HRM
HCM / HR / Travel | 85 | HR-AP | Initial Vendor Creation (HR review) |  | Master Data | 1 | [11 empty] | Business activity. Automatic HR review |  | Y |  | DBS FIN
HCM / HR / Travel | 86 | Core HR+ | Core HR setup |  | Setup | 1 | [11 empty] | Not a blocker for Financial Execution |  | Yes |  | DBS | Adil, Laia
Identity & Access
Identity & Access | 87 | Active Directory | Create new accounts + AD groups |  | Setup | 1 | [11 empty] | UNESDIR may auto-create following naming convention |  | Yes |  | DBS/OSM/NSO | C. Souvanthong
Identity & Access | 88 | Role Mgmt | Create Places |  | Config | 1 | [13 empty] | Yes |  | DBS | Dimitri
Identity & Access | 89 | Role Mgmt | Create users with appropriate roles under new places |  | Config | 1 | [11 empty] | Verify Payment approval invoice roles |  | Yes |  | FIN
Auth Roles
Auth Roles | 64 | SAP ROLE | Clone Y_*_* roles (~48) | PFCG / SUPC | Role | 4 | AGR_TIMEB, SPERS_OBJ, USR12, USR13, UST12 | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Y_XXXX_* pattern | 2026-04-10 | Y | Todo | DBS | P. Ikouna
Auth Roles | 65 | SAP ROLE | Assign roles to users | SU01 / SU10 | Role | 64 |  | — | — | — | — | — | — | — | — | — | — | Per env |  | Y | Manual
Auth Roles | 66 | SAP ROLE | Update F_BKPF_BUK values | PFCG | Role | 64 |  | — | — | — | — | — | — | — | — | — | — | Multi-BUKRS roles |  | Y | Manual
Master Data
Master Data | 67 | SAP FI-AP | Extend vendors to co code | FK01 / XK01 | Master Data | 1,4 |  | — | — | — | — | — | — | — | — | — | — | LFB1 per BUKRS |  | Y | Manual
Master Data | 68 | SAP FI-AR | Extend customers to co code | FD01 / XD01 | Master Data | 1,4 |  | — | — | — | — | — | — | — | — | — | — | KNB1 per BUKRS |  | Y | Manual
Activation
Activation | 69 | SAP FI | Open posting periods | OB52 | Config | 1 | T001B | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Not transported — per env |  | Y | Todo | FIN/FAS/FRA | J.La
Activation | 70 | SAP FI | Document + object number ranges | FBN1 / OBH2 | Config | 1 | NRIV | ✗ | ✗ | ∅ | ✗ | ∅ | ∅ | ∅ | ✗ | ✗ | ✗ | Per env |  | Y | Todo | DBS | P.Lopez
Activation | 71 | SAP FI-AA | Open AA period | OAAQ | Config | 46 | T093D | ✓ | ✓ | ∅ | ✓ | ∅ | ∅ | ∅ | ✓ | ✓ | ✓ | Per fiscal year |  | Y | Done
DUO Apllications
DUO Apllications | 78 | MOUV | Synchronize SAP Master Data |  | Sync | 1 | [11 empty] | 1 day |  | Yes |  |  | S. Dartigolle, R.Rios
DUO Apllications | 79 | CMT | Synchronize SAP Master Data |  | Sync | 1 | [11 empty] | 1 day |  | Yes |  | DBS | D. Andros
DUO Apllications | 92 | HR Workflow | Add new Sector |  | Config | 1 | [13 empty] | No |  | DBS | Naila
DUO Apllications | 93 | TULIP | Add new Sector |  | Config | 1 | [13 empty] | No |  | DBS | Naila
DUO Apllications | 94 | PROSPER | BFM impact actions |  | Config | 1 | [13 empty] | No |  | DBS | Naila
DUO Apllications | 95 | INFOSERV | In UNESDIR, modify Cost Center associated to Sector/Service |  | Config | 1 | [11 empty] | To be confirmed |  | TBD |  | DBS/IOP/TSU | Naila / Alessandra
DUO Apllications | 96 | REC | Update & review Application Role name + republish web app |  | Config | 1 | [13 empty] | No |  | DBS | S. Dartigolle
Testing
Testing | 72 | SAP FI | Test FI posting | FB50 | Test | all |  | — | — | — | — | — | — | — | — | — | — | FM + substitution check |  | Y | Manual
Testing | 73 | SAP FI | Test F110 payment | F110 | Test | 24,25 |  | — | — | — | — | — | — | — | — | — | — | Bank ranking check |  | Y | Manual
Testing | 74 | SAP FI | Test EBS import | FF.5 | Test | 19 |  | — | — | — | — | — | — | — | — | — | — | MT940 format |  | Y | Manual
Testing | 75 | SAP FM | Test budget + commitment | FMX1 / FMBB | Test | 8,50,51,52,53 |  | — | — | — | — | — | — | — | — | — | — | AVC verify |  | Y | Manual
Master Data Conversion
Master Data Conversion | 76 | Balance Conversion | Balance conversion (existing movements) |  | Conversion | 1 | [11 empty] | Business Activity. If institute has historical movements, decide migration approach |  | Y
Master Data Conversion | 77 | AP/AR | Open items AP/AR migration |  | Conversion | 1,4 | [11 empty] | Business Activity. Convert open AP/AR items |  | Y
PPM Success Factor
Planning | 90 | Core Planner | Set up Core Planner |  | Config | 1 | [11 empty] | Once done, proceed with items 21,22 if needed |  | Yes |  | DBS | A. Mercea
Planning | 91 | Core Manager | Set up Core Manager |  | Config | 1 | [13 empty] | No |  | DBS | A. Mercea
Communications & Documents
Comms | 98 | COUR(R)IER | Set exceptions to separate divisions for re-invoicing |  | Config | 1 | [13 empty] | Yes |  | DBS | C.Michiote
Comms | 99 | UNTERM | Update Terminology database |  | Config | 1 | [11 empty] | Check if Reference is updated |  | Yes |  | CLD/T
Comms | 100 | Smart | Configure Institute options |  | Config | 1 | [13 empty] | Yes |  | DBS | Narmin
Comms | 101 | SHAREPOINT | Rename SharePoint group or create new |  | Config | 1 | [13 empty] | Yes |  | DBS | C.Michiote
Comms | 102 | UNESDOC | Check that replication job takes new name into account |  | Config | 1 | [11 empty] | For FO/institute |  | No |  | DBS | ?
Comms | 103 | WATCHDOC | Implement specific groups for re-invoicing |  | Config | 1 | [13 empty] | Yes |  | DBS | R. Lévy
Comms | 104 | OURDRIVE | Implement the new Model Filing Plan |  | Config | 1 | [13 empty] | Yes |  | DBS | Imad

## STEM Inventory
Transport | Date | Owner | FN | Desc | PGMID | OBJECT | OBJ_NAME | Keys | Sample TABKEY | Explanation | Maps to Golden Step
D01K9B0CDS | 2024-11-14 | A_SEFIANI | Q | HR - PA task (D01K9B0CDR) | R3TR | TABU | T500P | 1 | 350CN09 | HR / Travel personnel config | #58 Personnel area
D01K9B0CDS | 2024-11-14 | A_SEFIANI | Q | HR - PA task (D01K9B0CDR) | R3TR | TDAT | ADDRESS | 0 |  | Address tables bundle (ADR2..ADR13, ADRC...)
D01K9B0CDS | 2024-11-14 | A_SEFIANI | Q | HR - PA task (D01K9B0CDR) | R3TR | TDAT | ADDRESS_4.6 | 0 |  | Transport data bundle ADDRESS_4.6
D01K9B0CDS | 2024-11-14 | A_SEFIANI | Q | HR - PA task (D01K9B0CDR) | R3TR | VDAT | V_T001P | 0 |  | View data V_T001P
D01K9B0CDS | 2024-11-14 | A_SEFIANI | Q | HR - PA task (D01K9B0CDR) | R3TR | VDAT | V_001P_ALL | 0 |  | View data V_001P_ALL
D01K9B0CDS | 2024-11-14 | A_SEFIANI | Q | HR - PA task (D01K9B0CDR) | R3TR | VDAT | V_T7UNPAD_DS0P | 0 |  | View data V_T7UNPAD_DS0P
D01K9B0CDS | 2024-11-14 | A_SEFIANI | Q | HR - PA task (D01K9B0CDR) | R3TR | TABU | T527O | 16 | 3501CN09SHAADM; 3501CN09SHABFM | HR personnel customizing | #80 HCM customizing
D01K9B0CDS | 2024-11-14 | A_SEFIANI | Q | HR - PA task (D01K9B0CDR) | R3TR | CDAT | T778V | 0 |  | Customer table data T778V
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FM01_A | 0 |  | View data V_FM01_A
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_001_B | 0 |  | View data V_001_B
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | TDAT | ADDRESS | 0 |  | Address tables bundle (ADR2..ADR13, ADRC...)
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | TDAT | ADDRESS_4.6 | 0 |  | Transport data bundle ADDRESS_4.6
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FMHIVAR | 0 |  | View data V_FMHIVAR
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FM01_H | 0 |  | View data V_FM01_H
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FM01_C | 0 |  | View data V_FM01_C
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FMUP00_F | 0 |  | View data V_FMUP00_F
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FM01D_F | 0 |  | View data V_FM01D_F
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FMFUNDTYPE | 0 |  | View data V_FMFUNDTYPE | #6 Fund types maintenance
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FMDIMSTATE | 0 |  | View data V_FMDIMSTATE
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FMBUDCAT | 0 |  | View data V_FMBUDCAT
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | CDAT | VC_FMBUDTYPE | 0 |  | Customer table data VC_FMBUDTYPE
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FMPTCOMBS | 0 |  | View data V_FMPTCOMBS
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | CDAT | VC_FMSTATUS | 0 |  | Customer table data VC_FMSTATUS
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FMAVCLDGRATT | 0 |  | View data V_FMAVCLDGRATT
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FMBCSA | 0 |  | View data V_FMBCSA
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | CDAT | VC_FMAVCBUDFILT1 | 0 |  | Customer table data VC_FMAVCBUDFILT1
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FMAVCLDGRGAT | 0 |  | View data V_FMAVCLDGRGAT
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FMAVCLDGRACT | 0 |  | View data V_FMAVCLDGRACT
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_T001_FMACT | 0 |  | View data V_T001_FMACT
D01K9B0F3W | 2026-04-14 | I_KONAKOV | Q | FM task (D01K9B0F3V) | R3TR | VDAT | V_FMIUR | 0 |  | View data V_FMIUR
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_T024E | 0 |  | View data V_T024E
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_T001W | 0 |  | View data V_T001W
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | TDAT | ADDRESS | 0 |  | Address tables bundle (ADR2..ADR13, ADRC...)
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | TDAT | ADDRESS_4.6 | 0 |  | Transport data bundle ADDRESS_4.6
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_T024E_ASSIGN | 0 |  | View data V_T024E_ASSIGN
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | W_T024W_ASSIGN | 0 |  | View data W_T024W_ASSIGN
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_T399I | 0 |  | View data V_T399I
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_T001W_I | 0 |  | View data V_T001W_I
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_024 | 0 |  | View data V_024
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_TCJ41 | 0 |  | View data V_TCJ41
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_T024I | 0 |  | View data V_T024I
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_T001K_ASSIGN | 0 |  | View data V_T001K_ASSIGN
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | TDAT | ADDRESS | 0 |  | Address tables bundle (ADR2..ADR13, ADRC...)
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | TDAT | ADDRESS_4.6 | 0 |  | Transport data bundle ADDRESS_4.6
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_T16FG_2 | 0 |  | View data V_T16FG_2
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | VV_T16FC_2 | 0 |  | View data VV_T16FC_2
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_T16FG_3 | 0 |  | View data V_T16FG_3
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | VV_T16FC_3 | 0 |  | View data VV_T16FC_3
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_001K_K | 0 |  | View data V_001K_K
D01K9B0F41 | 2026-04-14 | R_RIOS | Q | Logistic task (D01K9B0F40) | R3TR | VDAT | V_TBPFD_P | 0 |  | View data V_TBPFD_P
D01K9B0F4I | 2026-04-14 | R_RIOS | Q | FI periods (D01K9B0CBF) | R3TR | VDAT | V_T010O | 0 |  | View data V_T010O
D01K9B0F4I | 2026-04-14 | R_RIOS | Q | FI periods (D01K9B0CBF) | R3TR | VDAT | V_T001B | 0 |  | View data V_T001B
D01K9B0F4I | 2026-04-14 | R_RIOS | Q | FI periods (D01K9B0CBF) | R3TR | VDAT | V_001_R | 0 |  | View data V_001_R
D01K9B0F4I | 2026-04-14 | R_RIOS | Q | FI periods (D01K9B0CBF) | R3TR | TABU | NRIV | 1 | 350RK_BELEG MGIE * | Customizing table NRIV
D01K9B0F4I | 2026-04-14 | R_RIOS | Q | FI periods (D01K9B0CBF) | R3TR | TABU | TNRGT | 44 | 3500RK_BELEG MGIE *; 3501RK_BELEG MGIE * | Customizing table TNRGT
D01K9B0F4I | 2026-04-14 | R_RIOS | Q | FI periods (D01K9B0CBF) | R3TR | CDAT | VC_T030K | 0 |  | Customer table data VC_T030K
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | AAACC_OBJ | 7 | 350STEM01FISTL * 01; 350STEM01FISTL * 02 | Asset accounting config | #43 Account assignment objects
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | ATPRA | 1 | 350STEM | Asset accounting config | #46 Asset transfer
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | MARV | 1 | 350STEM | Customizing table MARV | #46 MM/AA period
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | SKB1 | 639 | 350STEM0001044711; 350STEM0001044714 | GL accounts at company-code level | #4 Extend GL per co code
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T001 | 4 | 350STEM; 350STEM | Company code core record (T001 family) | #1 Create / Copy Company Code
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T001Q | 2 | 350STEM0002; 350STEM0002 | Company code core record (T001 family) | #1 Create / Copy Company Code
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T012 | 1 | 350STEMCBE01 | House bank / bank account / bank text | #16 Create house banks
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T012D | 1 | 350STEMCBE01 | House bank / bank account / bank text | #16 Create house banks
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T012K | 3 | 350STEMCBE01ETB01; 350STEMCBE01ETB02 | House bank / bank account / bank text | #18 Bank accounts
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T012T | 9 | 350ESTEMCBE01ETB01; 350ESTEMCBE01ETB02 | House bank / bank account / bank text | #16 Create house banks
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T035D | 3 | 350STEMCBE01-ETB1; 350STEMCBE01-ETB2 | Cash management planning groups | #28 Cash management planning groups
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T035U | 9 | 350ESTEMCBE01-ETB1; 350ESTEMCBE01-ETB2 | Cash management planning groups | #28 Cash management planning groups
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T042 | 1 | 350STEM | FBZP payment program config | #20 FBZP — All co codes
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T042B | 1 | 350STEM | FBZP payment program config | #23 Payment methods per co code
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T042E | 3 | 350STEMM; 350STEMO | FBZP payment program config | #22 Payment methods per country
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T042T | 1 | 350STEM | FBZP payment program config | #21 FBZP Paying co codes
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T043G | 1 | 350STEM | Tolerance group config | #35 Tolerance groups
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T043GT | 3 | 350ESTEM; 350FSTEM | Tolerance group config | #35 Tolerance groups
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T043S | 1 | 350STEM | Tolerance group config | #35 Tolerance groups
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T043ST | 3 | 350ESTEM; 350FSTEM | Tolerance group config | #35 Tolerance groups
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T043T | 13 | 350 STEM; 3500005STEM | Tolerance group config | #35 Tolerance groups
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T047 | 1 | 350STEM | Dunning procedure assignment | #42 Dunning procedure
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T093B | 3 | 350STEM01; 350STEM02 | Asset accounting config | #44 Asset class → GL determination
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T093C | 1 | 350STEM | Asset accounting config | #43 Chart of depreciation assignment
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T093D | 1 | 350STEM01 | Asset accounting config | #46 Asset transfer date
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T093U | 3 | 350STEM02; 350STEM04 | Asset accounting config | #45 Depreciation keys
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T093V | 2 | 350STEMA0030001; 350STEMA0100001 | Asset accounting config | #43 Chart of depreciation
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T169G | 13 | 350STEMAN; 350STEMAP | Tolerance group config | #37 MM/IV tolerances
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T169P | 1 | 350STEM | Tolerance group config | #37 MM/IV tolerances
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T169V | 1 | 350STEM | Tolerance group config | #37 MM/IV tolerances
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | T882 | 4 | 350STEM00; 350STEM00 | Consolidation unit | #55 Consolidation unit
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TDAT | ADDRESS | 0 |  | Address tables bundle (ADR2..ADR13, ADRC...)
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TDAT | ADDRESS_4.6 | 0 |  | Transport data bundle ADDRESS_4.6
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | VDAT | V_T001 | 0 |  | View data V_T001
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | CDAT | CAREAMAINT | 0 |  | Customer table data CAREAMAINT
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | VDAT | V_T001A | 0 |  | View data V_T001A
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | VDAT | V_T001 | 0 |  | View data V_T001
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TDAT | ADDRESS | 0 |  | Address tables bundle (ADR2..ADR13, ADRC...)
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TDAT | ADDRESS_4.6 | 0 |  | Transport data bundle ADDRESS_4.6
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | SKB1 | 639 | 350STEM0001044711; 350STEM0001044714 | GL accounts at company-code level | #4 Extend GL per co code
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | TABU | CSKB | 359 | 350STEM000406110024001231; 350STEM000406210024001231 | CO master data (cost element/center) | #11 Cost elements per CO area
D01K9B0CBG | 2026-04-15 | JP_LOPEZ | Q | FI task (D01K9B0CBF) — our SKB1+CSKB work | R3TR | VDAT | V_T001Q | 0 |  | View data V_T001Q
D01K9B0F7J | 2026-04-15 | JP_LOPEZ | S | Workbench task (D01K9B0F7I) | R3TR | TDAT | GGB1 | 0 |  | GGB1 substitution bundle (carries GB90/921/922/T) | #29 GGB1 substitution bundle
D01K9B0F7J | 2026-04-15 | JP_LOPEZ | S | Workbench task (D01K9B0F7I) | R3TR | TABU | GB01C | 1 | 350* | Validation/Substitution rule (GGB0/GGB1 family)
D01K9B0F7J | 2026-04-15 | JP_LOPEZ | S | Workbench task (D01K9B0F7I) | R3TR | TABU | GB02C | 1 | * | Validation/Substitution rule (GGB0/GGB1 family)

## MGIE Inventory
Transport | PGMID | OBJECT | OBJ_NAME | Keys | Explanation | Maps to Golden Step
D01K9A00FB | CORR | RELE | D01K9A00FC 20130204 155515 D_TAL | 0 | Released sub-task
D01K9A00FB | CORR | RELE | D01K9A00FD 20130205 144506 M_SPRONK | 0 | Released sub-task
D01K9A00FB | R3TR | TDAT | ADDRESS | 0 | Address tables bundle
D01K9A00FB | R3TR | TDAT | ADDRESS_4.6 | 0 | Address tables bundle
D01K9A00FB | R3TR | TDAT | GGB1 | 0 | GGB1 substitution bundle | #29 GGB1 substitution bundle
D01K9A00FB | R3TR | TDAT | GRW_SET | 0 | GS02 sets bundle
D01K9A00FB | R3TR | VDAT | V_001_B | 0 | View data V_001_B
D01K9A00FB | R3TR | VDAT | V_T001Q | 0 | View data V_T001Q
D01K9A00FB | R3TR | VDAT | V_TPIR2 | 0 | View data V_TPIR2
D01K9A00FB | R3TR | CDAT | VC_BANKDET | 0 | Customer data VC_BANKDET
D01K9A00FB | R3TR | VDAT | V_T042B | 0 | View data V_T042B
D01K9A00FB | R3TR | VDAT | V_T042E | 0 | View data V_T042E
D01K9A00FB | R3TR | CDAT | VC_T042ZL | 0 | Customer data VC_T042ZL
D01K9A00FB | R3TR | TABU | T003D | 4 | Customizing table T003D
D01K9A00FB | R3TR | VDAT | V_FMFUNDTYPE | 0 | View data V_FMFUNDTYPE | #6 Fund types maintenance
D01K9A00FB | R3TR | VDAT | V_001O_B | 0 | View data V_001O_B
D01K9A00FB | R3TR | VDAT | V_T001O | 0 | View data V_T001O
D01K9A00FB | R3TR | VDAT | V_T093C_08 | 0 | View data V_T093C_08
D01K9A00FB | R3TR | VDAT | V_T093C_03 | 0 | View data V_T093C_03
D01K9A00FB | R3TR | VDAT | V_FM01_C | 0 | View data V_FM01_C
D01K9A00FB | R3TR | VDAT | V_FM01_G | 0 | View data V_FM01_G
D01K9A00FB | R3TR | VDAT | V_FM01_H | 0 | View data V_FM01_H
D01K9A00FB | R3TR | VDAT | V_FM01_I | 0 | View data V_FM01_I
D01K9A00FB | R3TR | VDAT | V_FM01C | 0 | View data V_FM01C
D01K9A00FB | R3TR | VDAT | V_FMRE_HRBA | 0 | View data V_FMRE_HRBA
D01K9A00FB | R3TR | VDAT | V_T035D | 0 | View data V_T035D
D01K9A00FB | R3TR | VDAT | V_TCJ41 | 0 | View data V_TCJ41
D01K9A00FB | R3TR | VDAT | V_TBPFD_P | 0 | View data V_TBPFD_P
D01K9A00FB | R3TR | CDAT | VC_T012 | 0 | Customer data VC_T012
D01K9A00FB | R3TR | VDAT | V_005_E | 0 | View data V_005_E
D01K9A00FB | R3TR | VDAT | V_T001Q | 0 | View data V_T001Q
D01K9A00FB | R3TR | VDAT | V_T010O | 0 | View data V_T010O
D01K9A00FB | R3TR | VDAT | V_001_R | 0 | View data V_001_R
D01K9A00FB | R3TR | F01U | IBE MGIE | 0 | Cross-company clearing pair IBE MGIE
D01K9A00FB | R3TR | F01U | ICTPMGIE | 0 | Cross-company clearing pair ICTPMGIE
D01K9A00FB | R3TR | F01U | IIEPMGIE | 0 | Cross-company clearing pair IIEPMGIE
D01K9A00FB | R3TR | F01U | MGIEIBE | 0 | Cross-company clearing pair MGIEIBE
D01K9A00FB | R3TR | F01U | MGIEICTP | 0 | Cross-company clearing pair MGIEICTP
D01K9A00FB | R3TR | F01U | MGIEIIEP | 0 | Cross-company clearing pair MGIEIIEP
D01K9A00FB | R3TR | F01U | MGIEUBO | 0 | Cross-company clearing pair MGIEUBO
D01K9A00FB | R3TR | F01U | MGIEUIL | 0 | Cross-company clearing pair MGIEUIL
D01K9A00FB | R3TR | F01U | MGIEUIS | 0 | Cross-company clearing pair MGIEUIS
D01K9A00FB | R3TR | F01U | MGIEUNES | 0 | Cross-company clearing pair MGIEUNES
D01K9A00FB | R3TR | F01U | UBO MGIE | 0 | Cross-company clearing pair UBO MGIE
D01K9A00FB | R3TR | F01U | UIL MGIE | 0 | Cross-company clearing pair UIL MGIE
D01K9A00FB | R3TR | F01U | UIS MGIE | 0 | Cross-company clearing pair UIS MGIE
D01K9A00FB | R3TR | F01U | UNESMGIE | 0 | Cross-company clearing pair UNESMGIE
D01K9A00FB | R3TR | CDAT | VVC_T683_TX | 0 | Customer data VVC_T683_TX
D01K9A00FB | R3TR | CDAT | VERSION_A | 0 | Customer data VERSION_A
D01K9A00FB | R3TR | CDAT | CAREAMAINT | 0 | Customer data CAREAMAINT
D01K9A00FB | R3TR | CDAT | CAREAMAINT | 0 | Customer data CAREAMAINT
D01K9A00FB | R3TR | VDAT | V_FM01_A | 0 | View data V_FM01_A
D01K9A00FB | R3TR | VDAT | V_T001_FM | 0 | View data V_T001_FM
D01K9A00FB | R3TR | TABU | AAACC_OBJ | 7 | Asset accounting config | #43 Account assignment objects
D01K9A00FB | R3TR | TABU | MARV | 1 | Customizing table MARV | #46 MM/AA period
D01K9A00FB | R3TR | TABU | T001 | 7 | Company code core record | #1 Create / Copy Company Code
D01K9A00FB | R3TR | TABU | T001Q | 10 | Company code core record | #1 Create / Copy Company Code
D01K9A00FB | R3TR | TABU | T012 | 4 | House bank / bank account | #16 Create house banks
D01K9A00FB | R3TR | TABU | T012D | 4 | House bank / bank account | #16 Create house banks
D01K9A00FB | R3TR | TABU | T012K | 8 | House bank / bank account | #18 Bank accounts
D01K9A00FB | R3TR | TABU | T012T | 10 | House bank / bank account | #16 Create house banks
D01K9A00FB | R3TR | TABU | T035D | 6 | Cash management planning groups | #28 Cash management planning groups
D01K9A00FB | R3TR | TABU | T035U | 6 | Cash management planning groups | #28 Cash management planning groups
D01K9A00FB | R3TR | TABU | T042 | 1 | FBZP payment program config | #20 FBZP — All co codes
D01K9A00FB | R3TR | TABU | T042A | 16 | FBZP payment program config | #25 FBZP extras
D01K9A00FB | R3TR | TABU | T042B | 2 | FBZP payment program config | #23 Payment methods per co code
D01K9A00FB | R3TR | TABU | T042D | 6 | FBZP payment program config | #25 FBZP extras
D01K9A00FB | R3TR | TABU | T042E | 10 | FBZP payment program config | #22 Payment methods per country
D01K9A00FB | R3TR | TABU | T042I | 22 | FBZP payment program config | #24 Bank determination/ranking
D01K9A00FB | R3TR | TABU | T042T | 2 | FBZP payment program config | #21 FBZP Paying co codes
D01K9A00FB | R3TR | TABU | T042V | 10 | FBZP payment program config | #25 FBZP extras
D01K9A00FB | R3TR | TABU | T043G | 1 | Tolerance group config | #35 Tolerance groups
D01K9A00FB | R3TR | TABU | T043GT | 2 | Tolerance group config | #35 Tolerance groups
D01K9A00FB | R3TR | TABU | T043S | 1 | Tolerance group config | #35 Tolerance groups
D01K9A00FB | R3TR | TABU | T043ST | 2 | Tolerance group config | #35 Tolerance groups
D01K9A00FB | R3TR | TABU | T043T | 1 | Tolerance group config | #35 Tolerance groups
D01K9A00FB | R3TR | TABU | T047 | 1 | Dunning procedure | #42 Dunning procedure
D01K9A00FB | R3TR | TABU | T093B | 4 | Asset accounting config | #44 Asset class → GL determination
D01K9A00FB | R3TR | TABU | T093C | 3 | Asset accounting config | #43 Chart of depreciation assignment
D01K9A00FB | R3TR | TABU | T093D | 1 | Asset accounting config | #46 Asset transfer date
D01K9A00FB | R3TR | TABU | T093U | 3 | Asset accounting config | #45 Depreciation keys
D01K9A00FB | R3TR | TABU | T093V | 2 | Asset accounting config | #43 Chart of depreciation
D01K9A00FB | R3TR | TABU | T169G | 13 | Tolerance group config | #37 MM/IV tolerances
D01K9A00FB | R3TR | TABU | T169P | 1 | Tolerance group config | #37 MM/IV tolerances
D01K9A00FB | R3TR | TABU | T169V | 1 | Tolerance group config | #37 MM/IV tolerances
D01K9A00FB | R3TR | TABU | T882 | 3 | Consolidation unit | #55 Consolidation unit
D01K9A00FB | R3TR | TABU | TCJ_CJ_NAMES | 4 | Cash journal config | #56 Cash journal setup
D01K9A00FB | R3TR | TABU | TCJ_C_JOURNALS | 2 | Cash journal config | #56 Cash journal setup
D01K9A00FB | R3TR | TABU | TCJ_PRINT | 1 | Cash journal config | #56 Cash journal setup
D01K9A00FB | R3TR | TABU | TCJ_TRANSACTIONS | 6 | Cash journal config | #56 Cash journal setup
D01K9A00FB | R3TR | TABU | TCJ_TRANS_NAMES | 12 | Cash journal config | #56 Cash journal setup
D01K9A00FB | R3TR | TDAT | ADDRESS | 0 | Address tables bundle
D01K9A00FB | R3TR | TDAT | ADDRESS_4.6 | 0 | Address tables bundle
D01K9A00FB | R3TR | VDAT | V_T001 | 0 | View data V_T001
D01K9A00FB | R3TR | CDAT | CAREAMAINT | 0 | Customer data CAREAMAINT
D01K9A00FB | R3TR | CDAT | CAREAMAINT | 0 | Customer data CAREAMAINT
D01K9A00FB | R3TR | VDAT | V_FMHIVAR | 0 | View data V_FMHIVAR
D01K9A00FB | R3TR | VDAT | V_T001_FMACT | 0 | View data V_T001_FMACT
D01K9A00FB | R3TR | VDAT | V_TBPFE_M | 0 | View data V_TBPFE_M
D01K9A00FB | R3TR | VDAT | V_FM01G | 0 | View data V_FM01G
D01K9A00FB | R3TR | VDAT | V_FMUP00_F | 0 | View data V_FMUP00_F
D01K9A00FB | R3TR | VDAT | V_FM01D_F | 0 | View data V_FM01D_F
D01K9A00FB | R3TR | VDAT | V_FMCIVARNT | 0 | View data V_FMCIVARNT
D01K9B09U7 | CORR | RELE | D01K9B09U8 20221118 134618 N_MENARD | 0 | Released sub-task
D01K9B09U7 | R3TR | VDAT | YVT001_ORGEH | 0 | View data YVT001_ORGEH
D01K9B09U7 | R3TR | VDAT | YVT542A_DASH | 0 | View data YVT542A_DASH
D01K9B09U7 | R3TR | VDAT | ZVT9SCT | 0 | View data ZVT9SCT
M01K900019 | CORR | RELE | M01K900020 20160726 141220 AN_LEVEQUE | 0 | Released sub-task
M01K900019 | R3TR | VDAT | V_T001_FM3 | 0 | View data V_T001_FM3

## ICBA Inventory
Transport | PGMID | OBJECT | OBJ_NAME | Keys | Explanation | Maps to Golden Step
D01K9B0194 | CORR | RELE | D01K9B0195 20160809 161856 I_KONAKOV | 0 | Released sub-task
D01K9B0194 | CORR | RELE | D01K9B0197 20160808 134556 M_SPRONK | 0 | Released sub-task
D01K9B0194 | CORR | RELE | D01K9B0198 20160808 124328 R_RIOS | 0 | Released sub-task
D01K9B0194 | CORR | RELE | D01K9B0199 20160808 132023 S_ROCHA | 0 | Released sub-task
D01K9B0194 | CORR | RELE | D01K9B019K 20160808 155446 P_IKOUNA | 0 | Released sub-task
D01K9B0194 | CORR | RELE | D01K9B019M 20160808 135539 A_SEFIANI | 0 | Released sub-task
D01K9B0194 | R3TR | ACGR | Y_IBE_INTERCO | 0 | Authorization role Y_IBE_INTERCO
D01K9B0194 | R3TR | ACGR | Y_ICBA_ADMINISTRATION | 0 | Authorization role Y_ICBA_ADMINISTRATION
D01K9B0194 | R3TR | ACGR | Y_ICBA_CO_INST_MAINT | 0 | Authorization role Y_ICBA_CO_INST_MAINT
D01K9B0194 | R3TR | ACGR | Y_ICBA_CO_REPORTING | 0 | Authorization role Y_ICBA_CO_REPORTING
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_AP_BALANCES_COMPLETE | 0 | Authorization role Y_ICBA_FI_AP_BALANCES_COMPLETE
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_AP_INVOICE_VENDOR | 0 | Authorization role Y_ICBA_FI_AP_INVOICE_VENDOR
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_AP_MD_VENDOR | 0 | Authorization role Y_ICBA_FI_AP_MD_VENDOR
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_AP_PAYMENTS | 0 | Authorization role Y_ICBA_FI_AP_PAYMENTS
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_AR_BALANCES_COMPLETE | 0 | Authorization role Y_ICBA_FI_AR_BALANCES_COMPLETE
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_AR_INVOICES_COMPLETE | 0 | Authorization role Y_ICBA_FI_AR_INVOICES_COMPLETE
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_AR_MASTER_DATA | 0 | Authorization role Y_ICBA_FI_AR_MASTER_DATA
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_ASSET_ACTIVATION | 0 | Authorization role Y_ICBA_FI_ASSET_ACTIVATION
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_ASSET_MASTER_DATA_AL | 0 | Authorization role Y_ICBA_FI_ASSET_MASTER_DATA_AL
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_ASSET_MASTER_DATA_CH | 0 | Authorization role Y_ICBA_FI_ASSET_MASTER_DATA_CH
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_ASSET_PERIODIC_PROCE | 0 | Authorization role Y_ICBA_FI_ASSET_PERIODIC_PROCE
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_ASSET_POSTING | 0 | Authorization role Y_ICBA_FI_ASSET_POSTING
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_ASSET_REPORTING | 0 | Authorization role Y_ICBA_FI_ASSET_REPORTING
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_CLOSING | 0 | Authorization role Y_ICBA_FI_CLOSING
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_FM_BU_APPROVAL | 0 | Authorization role Y_ICBA_FI_FM_BU_APPROVAL
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_FM_BU_CLOSING | 0 | Authorization role Y_ICBA_FI_FM_BU_CLOSING
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_FM_BU_REPORTING | 0 | Authorization role Y_ICBA_FI_FM_BU_REPORTING
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_FM_BU_RESERVE | 0 | Authorization role Y_ICBA_FI_FM_BU_RESERVE
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_FM_BU_UPDATE | 0 | Authorization role Y_ICBA_FI_FM_BU_UPDATE
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_FM_MD_STRUCTURE | 0 | Authorization role Y_ICBA_FI_FM_MD_STRUCTURE
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_GL_ACCT_REPORTING | 0 | Authorization role Y_ICBA_FI_GL_ACCT_REPORTING
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_GL_POSTINGS | 0 | Authorization role Y_ICBA_FI_GL_POSTINGS
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_TR_MASTER_DATA_DISP | 0 | Authorization role Y_ICBA_FI_TR_MASTER_DATA_DISP
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_TV_MASTER_DATA | 0 | Authorization role Y_ICBA_FI_TV_MASTER_DATA
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_TV_TRAVEL_ACCT | 0 | Authorization role Y_ICBA_FI_TV_TRAVEL_ACCT
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_TV_TRAVEL_MANAGER | 0 | Authorization role Y_ICBA_FI_TV_TRAVEL_MANAGER
D01K9B0194 | R3TR | ACGR | Y_ICBA_FI_TV_TRAVEL_REPORTING | 0 | Authorization role Y_ICBA_FI_TV_TRAVEL_REPORTING
D01K9B0194 | R3TR | ACGR | Y_ICBA_INTERCO | 0 | Authorization role Y_ICBA_INTERCO
D01K9B0194 | R3TR | ACGR | Y_ICBA_MM_CREATE_PO | 0 | Authorization role Y_ICBA_MM_CREATE_PO
D01K9B0194 | R3TR | ACGR | Y_ICBA_MM_CREATE_PR_INS | 0 | Authorization role Y_ICBA_MM_CREATE_PR_INS
D01K9B0194 | R3TR | ACGR | Y_ICBA_MM_GR_SES | 0 | Authorization role Y_ICBA_MM_GR_SES
D01K9B0194 | R3TR | ACGR | Y_ICBA_MM_INFOS_DISPLAY | 0 | Authorization role Y_ICBA_MM_INFOS_DISPLAY
D01K9B0194 | R3TR | ACGR | Y_ICBA_MM_MASTER_DATA | 0 | Authorization role Y_ICBA_MM_MASTER_DATA
D01K9B0194 | R3TR | ACGR | Y_ICBA_MM_RECEIPT | 0 | Authorization role Y_ICBA_MM_RECEIPT
D01K9B0194 | R3TR | ACGR | Y_ICBA_MM_VALIDATE_PO | 0 | Authorization role Y_ICBA_MM_VALIDATE_PO
D01K9B0194 | R3TR | ACGR | Y_ICBA_PS_MD_STRUCT_DISPLAY | 0 | Authorization role Y_ICBA_PS_MD_STRUCT_DISPLAY
D01K9B0194 | R3TR | ACGR | Y_ICBA_PS_MD_STRUCT_EXECUTE | 0 | Authorization role Y_ICBA_PS_MD_STRUCT_EXECUTE
D01K9B0194 | R3TR | ACGR | Y_ICBA_PS_MD_STRUCT_EXECUTE_BI | 0 | Authorization role Y_ICBA_PS_MD_STRUCT_EXECUTE_BI
D01K9B0194 | R3TR | ACGR | Y_ICBA_PS_REPORTING | 0 | Authorization role Y_ICBA_PS_REPORTING
D01K9B0194 | R3TR | ACGR | Y_IIEP_INTERCO | 0 | Authorization role Y_IIEP_INTERCO
D01K9B0194 | R3TR | ACGR | Y_MGIE_INTERCO | 0 | Authorization role Y_MGIE_INTERCO
D01K9B0194 | R3TR | ACGR | Y_UBO_INTERCO | 0 | Authorization role Y_UBO_INTERCO
D01K9B0194 | R3TR | ACGR | Y_UIL_INTERCO | 0 | Authorization role Y_UIL_INTERCO
D01K9B0194 | R3TR | ACGR | Y_UIS_INTERCO | 0 | Authorization role Y_UIS_INTERCO
D01K9B0194 | R3TR | ACGR | Y_UNES_INTERCO | 0 | Authorization role Y_UNES_INTERCO
D01K9B0194 | R3TR | CDAT | CAREAMAINT | 0 | Customer data CAREAMAINT
D01K9B0194 | R3TR | CDAT | VC_T012 | 0 | Customer data VC_T012
D01K9B0194 | R3TR | CDAT | VC_T028 | 0 | Customer data VC_T028
D01K9B0194 | R3TR | CDAT | VC_T042ZL | 0 | Customer data VC_T042ZL
D01K9B0194 | R3TR | CDAT | VERSION_A | 0 | Customer data VERSION_A
D01K9B0194 | R3TR | CDAT | VVC_T683_TX | 0 | Customer data VVC_T683_TX
D01K9B0194 | R3TR | CDAT | V_TKA3 | 0 | Customer data V_TKA3 | #10 CO versions
D01K9B0194 | R3TR | F01U | IBE ICBA | 0 | Cross-company clearing pair IBE ICBA
D01K9B0194 | R3TR | F01U | ICBAIBE | 0 | Cross-company clearing pair ICBAIBE
D01K9B0194 | R3TR | F01U | ICBAICTP | 0 | Cross-company clearing pair ICBAICTP
D01K9B0194 | R3TR | F01U | ICBAIIEP | 0 | Cross-company clearing pair ICBAIIEP
D01K9B0194 | R3TR | F01U | ICBAMGIE | 0 | Cross-company clearing pair ICBAMGIE
D01K9B0194 | R3TR | F01U | ICBAUBO | 0 | Cross-company clearing pair ICBAUBO
D01K9B0194 | R3TR | F01U | ICBAUIL | 0 | Cross-company clearing pair ICBAUIL
D01K9B0194 | R3TR | F01U | ICBAUIS | 0 | Cross-company clearing pair ICBAUIS
D01K9B0194 | R3TR | F01U | ICBAUNES | 0 | Cross-company clearing pair ICBAUNES
D01K9B0194 | R3TR | F01U | ICTPICBA | 0 | Cross-company clearing pair ICTPICBA
D01K9B0194 | R3TR | F01U | IIEPICBA | 0 | Cross-company clearing pair IIEPICBA
D01K9B0194 | R3TR | F01U | MGIEICBA | 0 | Cross-company clearing pair MGIEICBA
D01K9B0194 | R3TR | F01U | UBO ICBA | 0 | Cross-company clearing pair UBO ICBA
D01K9B0194 | R3TR | F01U | UIL ICBA | 0 | Cross-company clearing pair UIL ICBA
D01K9B0194 | R3TR | F01U | UIS ICBA | 0 | Cross-company clearing pair UIS ICBA
D01K9B0194 | R3TR | F01U | UNESICBA | 0 | Cross-company clearing pair UNESICBA
D01K9B0194 | R3TR | F30 | UNESGBB | 0 | F30 UNESGBB
D01K9B0194 | R3TR | F30 | UNESWRX | 0 | F30 UNESWRX
D01K9B0194 | R3TR | FTXP | TAXET V0 | 0 | FTXP TAXET V0
D01K9B0194 | R3TR | FTXP | TAXET V2 | 0 | FTXP TAXET V2
D01K9B0194 | R3TR | FTXP | TAXET VX | 0 | FTXP TAXET VX
D01K9B0194 | R3TR | TABU | AAACC_OBJ | 7 | Asset accounting config | #43 Account assignment objects
D01K9B0194 | R3TR | TABU | AGR_TIMEB | 49 | Customizing table AGR_TIMEB
D01K9B0194 | R3TR | TABU | MARV | 1 | Customizing table MARV | #46 MM/AA period
D01K9B0194 | R3TR | TABU | NRIV | 2 | Customizing table NRIV
D01K9B0194 | R3TR | TABU | NRIV | 2 | Customizing table NRIV
D01K9B0194 | R3TR | TABU | SKB1 | 575 | GL accounts at company-code level | #4 Extend GL per co code
D01K9B0194 | R3TR | TABU | SPERS_OBJ | 49 | Customizing table SPERS_OBJ
D01K9B0194 | R3TR | TABU | T001 | 6 | Company code core record | #1 Create / Copy Company Code
D01K9B0194 | R3TR | TABU | T001P | 5 | Customizing table T001P
D01K9B0194 | R3TR | TABU | T001Q | 2 | Company code core record | #1 Create / Copy Company Code
D01K9B0194 | R3TR | TABU | T003D | 3 | Customizing table T003D
D01K9B0194 | R3TR | TABU | T007V | 1 | Tax code config | #38 Tax codes
D01K9B0194 | R3TR | TABU | T012 | 3 | House bank / bank account | #16 Create house banks
D01K9B0194 | R3TR | TABU | T012D | 3 | House bank / bank account | #16 Create house banks
D01K9B0194 | R3TR | TABU | T012K | 6 | House bank / bank account | #18 Bank accounts
D01K9B0194 | R3TR | TABU | T012T | 6 | House bank / bank account | #16 Create house banks
D01K9B0194 | R3TR | TABU | T035D | 6 | Cash management planning groups | #28 Cash management planning groups
D01K9B0194 | R3TR | TABU | T035U | 6 | Cash management planning groups | #28 Cash management planning groups
D01K9B0194 | R3TR | TABU | T042 | 1 | FBZP payment program config | #20 FBZP — All co codes
D01K9B0194 | R3TR | TABU | T042B | 1 | FBZP payment program config | #23 Payment methods per co code
D01K9B0194 | R3TR | TABU | T042E | 3 | FBZP payment program config | #22 Payment methods per country
D01K9B0194 | R3TR | TABU | T042T | 1 | FBZP payment program config | #21 FBZP Paying co codes
D01K9B0194 | R3TR | TABU | T043G | 1 | Tolerance group config | #35 Tolerance groups
D01K9B0194 | R3TR | TABU | T043GT | 2 | Tolerance group config | #35 Tolerance groups
D01K9B0194 | R3TR | TABU | T043S | 1 | Tolerance group config | #35 Tolerance groups
D01K9B0194 | R3TR | TABU | T043ST | 2 | Tolerance group config | #35 Tolerance groups
D01K9B0194 | R3TR | TABU | T043T | 2 | Tolerance group config | #35 Tolerance groups
D01K9B0194 | R3TR | TABU | T047 | 1 | Dunning procedure | #42 Dunning procedure
D01K9B0194 | R3TR | TABU | T093B | 3 | Asset accounting config | #44 Asset class → GL determination
D01K9B0194 | R3TR | TABU | T093C | 2 | Asset accounting config | #43 Chart of depreciation assignment
D01K9B0194 | R3TR | TABU | T093D | 1 | Asset accounting config | #46 Asset transfer date
D01K9B0194 | R3TR | TABU | T093U | 3 | Asset accounting config | #45 Depreciation keys
D01K9B0194 | R3TR | TABU | T093V | 3 | Asset accounting config | #43 Chart of depreciation
D01K9B0194 | R3TR | TABU | T169G | 13 | Tolerance group config | #37 MM/IV tolerances
D01K9B0194 | R3TR | TABU | T169P | 1 | Tolerance group config | #37 MM/IV tolerances
D01K9B0194 | R3TR | TABU | T169V | 1 | Tolerance group config | #37 MM/IV tolerances
D01K9B0194 | R3TR | TABU | T500P | 2 | HR / Travel personnel config | #58 Personnel area
D01K9B0194 | R3TR | TABU | T7UNPAD_DS0P | 3 | Customizing table T7UNPAD_DS0P
D01K9B0194 | R3TR | TABU | T882 | 3 | Consolidation unit | #55 Consolidation unit
D01K9B0194 | R3TR | TABU | TCJ_CJ_NAMES | 4 | Cash journal config | #56 Cash journal setup
D01K9B0194 | R3TR | TABU | TCJ_C_JOURNALS | 2 | Cash journal config | #56 Cash journal setup
D01K9B0194 | R3TR | TABU | TCJ_PRINT | 1 | Cash journal config | #56 Cash journal setup
D01K9B0194 | R3TR | TABU | TCJ_TRANSACTIONS | 6 | Cash journal config | #56 Cash journal setup
D01K9B0194 | R3TR | TABU | TCJ_TRANS_NAMES | 12 | Cash journal config | #56 Cash journal setup
D01K9B0194 | R3TR | TABU | USR10 | 49 | Customizing table USR10
D01K9B0194 | R3TR | TABU | USR11 | 51 | Customizing table USR11
D01K9B0194 | R3TR | TABU | USR12 | 1256 | Customizing table USR12
D01K9B0194 | R3TR | TABU | USR13 | 1232 | Customizing table USR13
D01K9B0194 | R3TR | TABU | UST10S | 49 | Customizing table UST10S
D01K9B0194 | R3TR | TABU | UST12 | 1256 | Customizing table UST12
D01K9B0194 | R3TR | TDAT | ADDRESS | 0 | Address tables bundle
D01K9B0194 | R3TR | TDAT | ADDRESS | 0 | Address tables bundle
D01K9B0194 | R3TR | TDAT | ADDRESS | 0 | Address tables bundle
D01K9B0194 | R3TR | TDAT | ADDRESS | 0 | Address tables bundle
D01K9B0194 | R3TR | TDAT | ADDRESS_4.6 | 0 | Address tables bundle
D01K9B0194 | R3TR | TDAT | ADDRESS_4.6 | 0 | Address tables bundle
D01K9B0194 | R3TR | TDAT | ADDRESS_4.6 | 0 | Address tables bundle
D01K9B0194 | R3TR | TDAT | ADDRESS_4.6 | 0 | Address tables bundle
D01K9B0194 | R3TR | VDAT | V_001K_K | 0 | View data V_001K_K
D01K9B0194 | R3TR | VDAT | V_001O_B | 0 | View data V_001O_B
D01K9B0194 | R3TR | VDAT | V_001_B | 0 | View data V_001_B
D01K9B0194 | R3TR | VDAT | V_001_R | 0 | View data V_001_R
D01K9B0194 | R3TR | VDAT | V_005_E | 0 | View data V_005_E
D01K9B0194 | R3TR | VDAT | V_024 | 0 | View data V_024
D01K9B0194 | R3TR | VDAT | V_T001 | 0 | View data V_T001
D01K9B0194 | R3TR | VDAT | V_T001B | 0 | View data V_T001B
D01K9B0194 | R3TR | VDAT | V_T001K_ASSIGN | 0 | View data V_T001K_ASSIGN
D01K9B0194 | R3TR | VDAT | V_T001O | 0 | View data V_T001O
D01K9B0194 | R3TR | VDAT | V_T001P | 0 | View data V_T001P
D01K9B0194 | R3TR | VDAT | V_T001Q | 0 | View data V_T001Q
D01K9B0194 | R3TR | VDAT | V_T001W | 0 | View data V_T001W
D01K9B0194 | R3TR | VDAT | V_T001_FM3 | 0 | View data V_T001_FM3
D01K9B0194 | R3TR | VDAT | V_T010O | 0 | View data V_T010O
D01K9B0194 | R3TR | VDAT | V_T024E | 0 | View data V_T024E
D01K9B0194 | R3TR | VDAT | V_T024E_ASSIGN | 0 | View data V_T024E_ASSIGN
D01K9B0194 | R3TR | VDAT | V_T035D | 0 | View data V_T035D
D01K9B0194 | R3TR | VDAT | V_T093C_03 | 0 | View data V_T093C_03
D01K9B0194 | R3TR | VDAT | V_T093V | 0 | View data V_T093V
D01K9B0194 | R3TR | VDAT | V_T500P | 0 | View data V_T500P
D01K9B0194 | R3TR | VDAT | V_T7UNPAD_DS0P | 0 | View data V_T7UNPAD_DS0P
D01K9B0194 | R3TR | VDAT | V_TFTE_BSM_CUST | 0 | View data V_TFTE_BSM_CUST
D01K9B0194 | R3TR | VDAT | W_T024W_ASSIGN | 0 | View data W_T024W_ASSIGN
D01K9B01A5 | CORR | RELE | D01K9B01A6 20160808 132029 S_ROCHA | 0 | Released sub-task
D01K9B01A5 | R3TR | VDAT | V_TCJ41 | 0 | View data V_TCJ41
D01K9B01A5 | R3TR | VDAT | V_FMFUNDTYPE | 0 | View data V_FMFUNDTYPE | #6 Fund types maintenance
D01K9B01A5 | R3TR | VDAT | V_FM01_G | 0 | View data V_FM01_G
D01K9B01A5 | R3TR | VDAT | V_FM01_H | 0 | View data V_FM01_H
D01K9B01A5 | R3TR | VDAT | V_FM01_I | 0 | View data V_FM01_I
D01K9B01A5 | R3TR | VDAT | V_FM01_L | 0 | View data V_FM01_L
D01K9B01A5 | R3TR | VDAT | V_FMZUCO | 0 | View data V_FMZUCO
D01K9B01A5 | R3TR | VDAT | V_TBPFD_P | 0 | View data V_TBPFD_P
D01K9B01A5 | R3TR | VDAT | V_FM01_A | 0 | View data V_FM01_A
D01K9B01A5 | R3TR | VDAT | V_FMHIVAR | 0 | View data V_FMHIVAR
D01K9B01A5 | R3TR | VDAT | V_T001_FMACT | 0 | View data V_T001_FMACT
D01K9B01A5 | R3TR | VDAT | V_TBPFE_M | 0 | View data V_TBPFE_M
D01K9B01A5 | R3TR | VDAT | V_FM01G | 0 | View data V_FM01G
D01K9B01A5 | R3TR | VDAT | V_FMUP00_F | 0 | View data V_FMUP00_F
D01K9B01A5 | R3TR | VDAT | V_FMCIVARNT | 0 | View data V_FMCIVARNT
D01K9B01PP | CORR | RELE | D01K9B01PQ 20161115 103830 S_ROCHA | 0 | Released sub-task
D01K9B01PP | R3TR | VDAT | V_TREVBUKRS | 0 | View data V_TREVBUKRS
D01K9B09U7 | CORR | RELE | D01K9B09U8 20221118 134618 N_MENARD | 0 | Released sub-task
D01K9B09U7 | R3TR | VDAT | YVT001_ORGEH | 0 | View data YVT001_ORGEH
D01K9B09U7 | R3TR | VDAT | YVT542A_DASH | 0 | View data YVT542A_DASH
D01K9B09U7 | R3TR | VDAT | ZVT9SCT | 0 | View data ZVT9SCT
M01K900019 | CORR | RELE | M01K900020 20160726 141220 AN_LEVEQUE | 0 | Released sub-task
M01K900019 | R3TR | VDAT | V_T001_FM3 | 0 | View data V_T001_FM3
P01K950173 | CORR | RELE | P01K950174 20170324 160413 I_KONAKOV | 0 | Released sub-task
P01K950173 | R3TR | CDAT | VC_T028 | 0 | Customer data VC_T028
P01K950173 | R3TR | TDAT | ADDRESS | 0 | Address tables bundle
P01K950173 | R3TR | TDAT | ADDRESS_4.6 | 0 | Address tables bundle
P01K950173 | R3TR | VDAT | V_001_B | 0 | View data V_001_B
P01K950174 | R3TR | CDAT | VC_T028 | 0 | Customer data VC_T028
P01K950174 | R3TR | TDAT | ADDRESS | 0 | Address tables bundle
P01K950174 | R3TR | TDAT | ADDRESS_4.6 | 0 | Address tables bundle
P01K950174 | R3TR | VDAT | V_001_B | 0 | View data V_001_B
P01K950280 | R3TR | VDAT | V_001_B | 0 | View data V_001_B
P01K950280 | R3TR | TDAT | ADDRESS | 0 | Address tables bundle
P01K950280 | R3TR | TDAT | ADDRESS_4.6 | 0 | Address tables bundle

## ICTP Inventory
Transport | PGMID | OBJECT | OBJ_NAME | Keys | Explanation | Maps to Golden Step
D01K9B01GL | R3TR | TABU | ADR10 | 1 | Customizing table ADR10
D01K9B01GL | R3TR | TABU | ADR10S2 | 1 | Customizing table ADR10S2
D01K9B01GL | R3TR | TABU | ADR11 | 1 | Customizing table ADR11
D01K9B01GL | R3TR | TABU | ADR11S2 | 1 | Customizing table ADR11S2
D01K9B01GL | R3TR | TABU | ADR12 | 1 | Customizing table ADR12
D01K9B01GL | R3TR | TABU | ADR12S2 | 1 | Customizing table ADR12S2
D01K9B01GL | R3TR | TABU | ADR13 | 1 | Customizing table ADR13
D01K9B01GL | R3TR | TABU | ADR13S2 | 1 | Customizing table ADR13S2
D01K9B01GL | R3TR | TABU | ADR2 | 1 | Customizing table ADR2
D01K9B01GL | R3TR | TABU | ADR2S2 | 1 | Customizing table ADR2S2
D01K9B01GL | R3TR | TABU | ADR3 | 1 | Customizing table ADR3
D01K9B01GL | R3TR | TABU | ADR3S2 | 1 | Customizing table ADR3S2
D01K9B01GL | R3TR | TABU | ADR4 | 1 | Customizing table ADR4
D01K9B01GL | R3TR | TABU | ADR4S2 | 1 | Customizing table ADR4S2
D01K9B01GL | R3TR | TABU | ADR5 | 1 | Customizing table ADR5
D01K9B01GL | R3TR | TABU | ADR5S2 | 1 | Customizing table ADR5S2
D01K9B01GL | R3TR | TABU | ADR6 | 1 | Customizing table ADR6
D01K9B01GL | R3TR | TABU | ADR6S2 | 1 | Customizing table ADR6S2
D01K9B01GL | R3TR | TABU | ADR7 | 1 | Customizing table ADR7
D01K9B01GL | R3TR | TABU | ADR7S2 | 1 | Customizing table ADR7S2
D01K9B01GL | R3TR | TABU | ADR8 | 1 | Customizing table ADR8
D01K9B01GL | R3TR | TABU | ADR8S2 | 1 | Customizing table ADR8S2
D01K9B01GL | R3TR | TABU | ADR9 | 1 | Customizing table ADR9
D01K9B01GL | R3TR | TABU | ADR9S2 | 1 | Customizing table ADR9S2
D01K9B01GL | R3TR | TABU | ADRC | 1 | Customizing table ADRC
D01K9B01GL | R3TR | TABU | ADRCOMCS2 | 1 | Customizing table ADRCOMCS2
D01K9B01GL | R3TR | TABU | ADRCS2 | 1 | Customizing table ADRCS2
D01K9B01GL | R3TR | TABU | ADRCT | 1 | Customizing table ADRCT
D01K9B01GL | R3TR | TABU | ADRCTS2 | 1 | Customizing table ADRCTS2
D01K9B01GL | R3TR | TABU | ADRG | 1 | Customizing table ADRG
D01K9B01GL | R3TR | TABU | ADRGS2 | 1 | Customizing table ADRGS2
D01K9B01GL | R3TR | TABU | ADRT | 1 | Customizing table ADRT
D01K9B01GL | R3TR | TABU | ADRTS2 | 1 | Customizing table ADRTS2
D01K9B01GL | R3TR | TABU | ADRU | 1 | Customizing table ADRU
D01K9B01GL | R3TR | TABU | ADRUS2 | 1 | Customizing table ADRUS2
D01K9B01GL | R3TR | TABU | ADRV | 1 | Customizing table ADRV
D01K9B01GL | R3TR | TABU | T001 | 1 | Company code core record | #1 Create / Copy Company Code
D01K9B01GL | R3TR | TABU | T001P | 3 | Customizing table T001P
D01K9B01GL | R3TR | TABU | T500P | 2 | HR / Travel personnel config | #58 Personnel area
D01K9B01GL | R3TR | TABU | T7UNPAD_DS0P | 1 | Customizing table T7UNPAD_DS0P
D01K9B01GL | R3TR | TABU | T7UNPAD_DSDA | 1 | Customizing table T7UNPAD_DSDA
ICDK900002 | R3TR | TABU | ADR10 | 4 | Customizing table ADR10
ICDK900002 | R3TR | TABU | ADR10S2 | 4 | Customizing table ADR10S2
ICDK900002 | R3TR | TABU | ADR11 | 4 | Customizing table ADR11
ICDK900002 | R3TR | TABU | ADR11S2 | 4 | Customizing table ADR11S2
ICDK900002 | R3TR | TABU | ADR12 | 4 | Customizing table ADR12
ICDK900002 | R3TR | TABU | ADR12S2 | 4 | Customizing table ADR12S2
ICDK900002 | R3TR | TABU | ADR13 | 4 | Customizing table ADR13
ICDK900002 | R3TR | TABU | ADR13S2 | 4 | Customizing table ADR13S2
ICDK900002 | R3TR | TABU | ADR2 | 4 | Customizing table ADR2
ICDK900002 | R3TR | TABU | ADR2S2 | 4 | Customizing table ADR2S2
ICDK900002 | R3TR | TABU | ADR3 | 4 | Customizing table ADR3
ICDK900002 | R3TR | TABU | ADR3S2 | 4 | Customizing table ADR3S2
ICDK900002 | R3TR | TABU | ADR4 | 4 | Customizing table ADR4
ICDK900002 | R3TR | TABU | ADR4S2 | 4 | Customizing table ADR4S2
ICDK900002 | R3TR | TABU | ADR5 | 4 | Customizing table ADR5
ICDK900002 | R3TR | TABU | ADR5S2 | 4 | Customizing table ADR5S2
ICDK900002 | R3TR | TABU | ADR6 | 4 | Customizing table ADR6
ICDK900002 | R3TR | TABU | ADR6S2 | 4 | Customizing table ADR6S2
ICDK900002 | R3TR | TABU | ADR7 | 4 | Customizing table ADR7
ICDK900002 | R3TR | TABU | ADR7S2 | 4 | Customizing table ADR7S2
ICDK900002 | R3TR | TABU | ADR8 | 4 | Customizing table ADR8
ICDK900002 | R3TR | TABU | ADR8S2 | 4 | Customizing table ADR8S2
ICDK900002 | R3TR | TABU | ADR9 | 4 | Customizing table ADR9
ICDK900002 | R3TR | TABU | ADR9S2 | 4 | Customizing table ADR9S2
ICDK900002 | R3TR | TABU | ADRC | 4 | Customizing table ADRC
ICDK900002 | R3TR | TABU | ADRCOMCS2 | 4 | Customizing table ADRCOMCS2
ICDK900002 | R3TR | TABU | ADRCS2 | 4 | Customizing table ADRCS2
ICDK900002 | R3TR | TABU | ADRCT | 4 | Customizing table ADRCT
ICDK900002 | R3TR | TABU | ADRCTS2 | 4 | Customizing table ADRCTS2
ICDK900002 | R3TR | TABU | ADRG | 4 | Customizing table ADRG
ICDK900002 | R3TR | TABU | ADRGS2 | 4 | Customizing table ADRGS2
ICDK900002 | R3TR | TABU | ADRT | 4 | Customizing table ADRT
ICDK900002 | R3TR | TABU | ADRTS2 | 4 | Customizing table ADRTS2
ICDK900002 | R3TR | TABU | ADRU | 4 | Customizing table ADRU
ICDK900002 | R3TR | TABU | ADRUS2 | 4 | Customizing table ADRUS2
ICDK900002 | R3TR | TABU | ADRV | 4 | Customizing table ADRV
ICDK900002 | R3TR | TABU | AT10B | 14 | Customizing table AT10B
ICDK900002 | R3TR | TABU | AT80 | 48 | Customizing table AT80
ICDK900002 | R3TR | TABU | FM01 | 5 | Funds Management config | #5 FM area
ICDK900002 | R3TR | TABU | FM01C | 1 | Funds Management config
ICDK900002 | R3TR | TABU | FM01D | 1 | Funds Management config
ICDK900002 | R3TR | TABU | FM01G | 2 | Funds Management config
ICDK900002 | R3TR | TABU | FM01T | 2 | Funds Management config
ICDK900002 | R3TR | TABU | FMCFC0 | 1 | Funds Management config | #54 FM Carry-forward
ICDK900002 | R3TR | TABU | FMCFC1 | 54 | Funds Management config | #54 FM Carry-forward
ICDK900002 | R3TR | TABU | FMCFC2 | 31 | Funds Management config | #54 FM Carry-forward
ICDK900002 | R3TR | TABU | FMCIVARNT | 1 | Funds Management config
ICDK900002 | R3TR | TABU | FMCIVARNTT | 1 | Funds Management config
ICDK900002 | R3TR | TABU | FMFUNDTYPE | 6 | Funds Management config | #6 Fund types
ICDK900002 | R3TR | TABU | FMFUNDTYPET | 11 | Funds Management config
ICDK900002 | R3TR | TABU | FMHIVARNT | 1 | Funds Management config
ICDK900002 | R3TR | TABU | FMHIVARNTT | 1 | Funds Management config
ICDK900002 | R3TR | TABU | FMIUR | 14 | Funds Management config
ICDK900002 | R3TR | TABU | FMREAS_STRATS | 5 | Funds Management config
ICDK900002 | R3TR | TABU | MARV | 1 | Customizing table MARV | #46 MM/AA period
ICDK900002 | R3TR | TABU | NRIV | 5 | Customizing table NRIV
ICDK900002 | R3TR | TABU | SKB1 | 1720 | GL accounts at company-code level | #4 Extend GL per co code
ICDK900002 | R3TR | TABU | T001 | 6 | Company code core record | #1 Create / Copy Company Code
ICDK900002 | R3TR | TABU | T001A | 1 | Company code core record | #2 Add Group Currency
ICDK900002 | R3TR | TABU | T001B | 1 | Posting periods | #69 Open posting periods
ICDK900002 | R3TR | TABU | T001D | 2 | Customizing table T001D
ICDK900002 | R3TR | TABU | T001F | 3 | Customizing table T001F
ICDK900002 | R3TR | TABU | T001O | 2 | Customizing table T001O
ICDK900002 | R3TR | TABU | T001Q | 1 | Company code core record | #1 Create / Copy Company Code
ICDK900002 | R3TR | TABU | T001Z | 3 | Customizing table T001Z
ICDK900002 | R3TR | TABU | T003D | 5 | Customizing table T003D
ICDK900002 | R3TR | TABU | T010O | 1 | Posting periods | #69 Open posting periods
ICDK900002 | R3TR | TABU | T010P | 3 | Posting periods | #69 Open posting periods
ICDK900002 | R3TR | TABU | T012 | 289 | House bank / bank account | #16 Create house banks
ICDK900002 | R3TR | TABU | T012A | 16 | Customizing table T012A
ICDK900002 | R3TR | TABU | T012B | 90 | Customizing table T012B
ICDK900002 | R3TR | TABU | T012C | 60 | Customizing table T012C
ICDK900002 | R3TR | TABU | T012D | 289 | House bank / bank account | #16 Create house banks
ICDK900002 | R3TR | TABU | T012K | 554 | House bank / bank account | #18 Bank accounts
ICDK900002 | R3TR | TABU | T012T | 809 | House bank / bank account | #16 Create house banks
ICDK900002 | R3TR | TABU | T015W | 24 | Customizing table T015W
ICDK900002 | R3TR | TABU | T015WT | 24 | Customizing table T015WT
ICDK900002 | R3TR | TABU | T018C | 3 | Bank directory + bank type
ICDK900002 | R3TR | TABU | T018D | 1 | Bank directory + bank type
ICDK900002 | R3TR | TABU | T018V | 508 | Bank directory + bank type | #17 Bank directory entries
ICDK900002 | R3TR | TABU | T030H | 22 | GL automatic account determination | #14 OBA1 / Exchange rate diff
ICDK900002 | R3TR | TABU | T035D | 443 | Cash management planning groups | #28 Cash management planning groups
ICDK900002 | R3TR | TABU | T035U | 724 | Cash management planning groups | #28 Cash management planning groups
ICDK900002 | R3TR | TABU | T036V | 26 | Customizing table T036V
ICDK900002 | R3TR | TABU | T037R | 26 | Customizing table T037R
ICDK900002 | R3TR | TABU | T037S | 12 | Customizing table T037S
ICDK900002 | R3TR | TABU | T042 | 1 | FBZP payment program config | #20 FBZP — All co codes
ICDK900002 | R3TR | TABU | T042A | 128 | FBZP payment program config | #25 FBZP extras
ICDK900002 | R3TR | TABU | T042B | 2 | FBZP payment program config | #23 Payment methods per co code
ICDK900002 | R3TR | TABU | T042D | 58 | FBZP payment program config | #25 FBZP extras
ICDK900002 | R3TR | TABU | T042E | 44 | FBZP payment program config | #22 Payment methods per country
ICDK900002 | R3TR | TABU | T042I | 128 | FBZP payment program config | #24 Bank determination/ranking
ICDK900002 | R3TR | TABU | T042P | 1 | FBZP payment program config | #25 FBZP extras
ICDK900002 | R3TR | TABU | T042S | 1 | FBZP payment program config
ICDK900002 | R3TR | TABU | T042T | 2 | FBZP payment program config | #21 FBZP Paying co codes
ICDK900002 | R3TR | TABU | T042V | 32 | FBZP payment program config | #25 FBZP extras
ICDK900002 | R3TR | TABU | T042W | 9 | FBZP payment program config
ICDK900002 | R3TR | TABU | T042Y | 126 | FBZP payment program config
ICDK900002 | R3TR | TABU | T042Z | 22 | FBZP payment program config
ICDK900002 | R3TR | TABU | T042ZA | 12 | FBZP payment program config
ICDK900002 | R3TR | TABU | T043G | 1 | Tolerance group config | #35 Tolerance groups
ICDK900002 | R3TR | TABU | T043GT | 2 | Tolerance group config | #35 Tolerance groups
ICDK900002 | R3TR | TABU | T043S | 2 | Tolerance group config | #35 Tolerance groups
ICDK900002 | R3TR | TABU | T043ST | 3 | Tolerance group config | #35 Tolerance groups
ICDK900002 | R3TR | TABU | T043T | 2 | Tolerance group config | #35 Tolerance groups
ICDK900002 | R3TR | TABU | T045B | 6 | Customizing table T045B
ICDK900002 | R3TR | TABU | T045D | 4 | Customizing table T045D
ICDK900002 | R3TR | TABU | T045F | 4 | Customizing table T045F
ICDK900002 | R3TR | TABU | T045G | 4 | Customizing table T045G
ICDK900002 | R3TR | TABU | T045T | 2 | Customizing table T045T
ICDK900002 | R3TR | TABU | T046R | 54 | Customizing table T046R
ICDK900002 | R3TR | TABU | T046S | 18 | Customizing table T046S
ICDK900002 | R3TR | TABU | T047 | 1 | Dunning procedure | #42 Dunning procedure
ICDK900002 | R3TR | TABU | T047E | 5 | Customizing table T047E
ICDK900002 | R3TR | TABU | T077K | 6 | Customizing table T077K | #0 Vendor account groups
ICDK900002 | R3TR | TABU | T077Y | 6 | Customizing table T077Y
ICDK900002 | R3TR | TABU | T093B | 3 | Asset accounting config | #44 Asset class → GL determination
ICDK900002 | R3TR | TABU | T093C | 1 | Asset accounting config | #43 Chart of depreciation assignment
ICDK900002 | R3TR | TABU | T093D | 1 | Asset accounting config | #46 Asset transfer date
ICDK900002 | R3TR | TABU | T093SB | 1 | Asset accounting config
ICDK900002 | R3TR | TABU | T093U | 6 | Asset accounting config | #45 Depreciation keys
ICDK900002 | R3TR | TABU | T169B | 1 | Tolerance group config
ICDK900002 | R3TR | TABU | T169G | 13 | Tolerance group config | #37 MM/IV tolerances
ICDK900002 | R3TR | TABU | T169P | 1 | Tolerance group config | #37 MM/IV tolerances
ICDK900002 | R3TR | TABU | T169R | 1 | Tolerance group config
ICDK900002 | R3TR | TABU | T169V | 1 | Tolerance group config | #37 MM/IV tolerances
ICDK900002 | R3TR | TABU | T882 | 6 | Consolidation unit | #55 Consolidation unit
ICDK900002 | R3TR | TABU | TBAER | 1 | Customizing table TBAER
ICDK900002 | R3TR | TABU | TBP3A | 1 | Customizing table TBP3A
ICDK900002 | R3TR | TABU | TBP3B | 1 | Customizing table TBP3B
ICDK900002 | R3TR | TABU | TBPFE | 5 | Customizing table TBPFE
ICDK900002 | R3TR | TABU | TCJ_CJ_NAMES | 8 | Cash journal config | #56 Cash journal setup
ICDK900002 | R3TR | TABU | TCJ_C_JOURNALS | 4 | Cash journal config | #56 Cash journal setup
ICDK900002 | R3TR | TABU | TCJ_PRINT | 2 | Cash journal config | #56 Cash journal setup
ICDK900002 | R3TR | TABU | TCJ_TRANSACTIONS | 22 | Cash journal config | #56 Cash journal setup
ICDK900002 | R3TR | TABU | TCJ_TRANS_NAMES | 41 | Cash journal config | #56 Cash journal setup
ICDK900002 | R3TR | TABU | TCURY | 6 | Customizing table TCURY
ICDK900002 | R3TR | TABU | TIPZB | 1 | Customizing table TIPZB
ICDK900002 | R3TR | TABU | TKA3A | 22 | Controlling area config
ICDK900002 | R3TR | TABU | TKA3C | 42 | Controlling area config
ICDK900002 | R3TR | TABU | TPRCD | 2 | Customizing table TPRCD
ICDK900002 | R3TR | TABU | TRACC_ADDACCDATA | 15 | Customizing table TRACC_ADDACCDATA
ICDK900002 | R3TR | TABU | TRACC_MIG_AAREF | 12 | Customizing table TRACC_MIG_AAREF
ICDK900002 | R3TR | TABU | TZBZ | 1 | Customizing table TZBZ
ICDK900002 | R3TR | TABU | TZDEA | 3 | Customizing table TZDEA
ICDK900002 | R3TR | TABU | TZKN1 | 2 | Customizing table TZKN1
ICDK900002 | R3TR | TABU | TZKN2 | 12 | Customizing table TZKN2
ICDK900002 | R3TR | TABU | TZKN2T | 24 | Customizing table TZKN2T
ICDK900002 | R3TR | TABU | TZKN6 | 22 | Customizing table TZKN6
ICDK900002 | R3TR | TABU | TZKN7 | 11 | Customizing table TZKN7
ICDK900002 | R3TR | TABU | TZKN8 | 12 | Customizing table TZKN8
ICDK900002 | R3TR | TABU | TZKN8T | 24 | Customizing table TZKN8T
ICDK900002 | R3TR | TABU | TZPAB | 5 | Customizing table TZPAB
ICDK900004 | R3TR | TABU | T001 | 1 | Company code core record | #1 Create / Copy Company Code
ICDK900004 | R3TR | TABU | TKA00 | 2 | Controlling area config | #9 CO area
ICDK900004 | R3TR | TABU | TKA01 | 2 | Controlling area config | #9 CO area
ICDK900004 | R3TR | TABU | TKA02 | 1 | Controlling area config | #9 CO area assignment
ICDK900004 | R3TR | TABU | TKA07 | 7 | Controlling area config | #9 CO area
ICDK900004 | R3TR | TABU | TKA09 | 1 | Controlling area config | #9 CO area
ICDK900004 | R3TR | TABU | TKT09 | 1 | Customizing table TKT09 | #9 CO area text
ICDK900004 | R3TR | TABU | TKVS | 1 | Customizing table TKVS
ICDK900004 | R3TR | TABU | TKVST | 1 | Customizing table TKVST
ICDK900014 | R3TR | TABU | AAACC_OBJ | 1 | Asset accounting config | #43 Account assignment objects
ICDK900014 | R3TR | TABU | ANKB | 801 | Customizing table ANKB
ICDK900014 | R3TR | TABU | T001 | 1 | Company code core record | #1 Create / Copy Company Code
ICDK900014 | R3TR | TABU | T082AVIEWB | 27 | Customizing table T082AVIEWB
ICDK900014 | R3TR | TABU | T090A | 1 | Customizing table T090A
ICDK900014 | R3TR | TABU | T090NA | 18 | Customizing table T090NA
ICDK900014 | R3TR | TABU | T090NAT | 52 | Customizing table T090NAT
ICDK900014 | R3TR | TABU | T090NAZ | 26 | Customizing table T090NAZ
ICDK900014 | R3TR | TABU | T090ND | 5 | Customizing table T090ND
ICDK900014 | R3TR | TABU | T090NDT | 15 | Customizing table T090NDT
ICDK900014 | R3TR | TABU | T090NP | 4 | Customizing table T090NP
ICDK900014 | R3TR | TABU | T090NPT | 12 | Customizing table T090NPT
ICDK900014 | R3TR | TABU | T090NS | 12 | Customizing table T090NS
ICDK900014 | R3TR | TABU | T090NSG | 9 | Customizing table T090NSG
ICDK900014 | R3TR | TABU | T090NST | 27 | Customizing table T090NST
ICDK900014 | R3TR | TABU | T093 | 3 | Asset accounting config
ICDK900014 | R3TR | TABU | T093A | 3 | Asset accounting config
ICDK900014 | R3TR | TABU | T093B | 1 | Asset accounting config | #44 Asset class → GL determination
ICDK900014 | R3TR | TABU | T093B_RSL | 1 | Asset accounting config
ICDK900014 | R3TR | TABU | T093C | 1 | Asset accounting config | #43 Chart of depreciation assignment
ICDK900014 | R3TR | TABU | T093CE | 1 | Asset accounting config
ICDK900014 | R3TR | TABU | T093C_RSL | 1 | Asset accounting config
ICDK900014 | R3TR | TABU | T093D | 1 | Asset accounting config | #46 Asset transfer date
ICDK900014 | R3TR | TABU | T093N | 1 | Asset accounting config
ICDK900014 | R3TR | TABU | T093S | 45 | Asset accounting config
ICDK900014 | R3TR | TABU | T093T | 9 | Asset accounting config
ICDK900014 | R3TR | TABU | T093U | 1 | Asset accounting config | #45 Depreciation keys
ICDK900014 | R3TR | TABU | T093Y | 1 | Asset accounting config
ICDK900014 | R3TR | TABU | T096 | 2 | Customizing table T096
ICDK900014 | R3TR | TABU | T096T | 4 | Customizing table T096T
ICDK900014 | R3TR | TABU | TABWA | 4 | Customizing table TABWA
ICDK900014 | R3TR | TABU | TBPFE | 4 | Customizing table TBPFE
ICDK900014 | R3TR | TABU | TEUBWA | 1 | Customizing table TEUBWA
ICDK900014 | R3TR | TABU | TKKAJ | 9 | Customizing table TKKAJ
ICDK900014 | R3TR | TABU | TKKAL | 3 | Customizing table TKKAL
ICDK900093 | R3TR | TABU | ADR10 | 1 | Customizing table ADR10
ICDK900093 | R3TR | TABU | ADR10S2 | 1 | Customizing table ADR10S2
ICDK900093 | R3TR | TABU | ADR11 | 1 | Customizing table ADR11
ICDK900093 | R3TR | TABU | ADR11S2 | 1 | Customizing table ADR11S2
ICDK900093 | R3TR | TABU | ADR12 | 1 | Customizing table ADR12
ICDK900093 | R3TR | TABU | ADR12S2 | 1 | Customizing table ADR12S2
ICDK900093 | R3TR | TABU | ADR13 | 1 | Customizing table ADR13
ICDK900093 | R3TR | TABU | ADR13S2 | 1 | Customizing table ADR13S2
ICDK900093 | R3TR | TABU | ADR2 | 1 | Customizing table ADR2
ICDK900093 | R3TR | TABU | ADR2S2 | 1 | Customizing table ADR2S2
ICDK900093 | R3TR | TABU | ADR3 | 1 | Customizing table ADR3
ICDK900093 | R3TR | TABU | ADR3S2 | 1 | Customizing table ADR3S2
ICDK900093 | R3TR | TABU | ADR4 | 1 | Customizing table ADR4
ICDK900093 | R3TR | TABU | ADR4S2 | 1 | Customizing table ADR4S2
ICDK900093 | R3TR | TABU | ADR5 | 1 | Customizing table ADR5
ICDK900093 | R3TR | TABU | ADR5S2 | 1 | Customizing table ADR5S2
ICDK900093 | R3TR | TABU | ADR6 | 1 | Customizing table ADR6
ICDK900093 | R3TR | TABU | ADR6S2 | 1 | Customizing table ADR6S2
ICDK900093 | R3TR | TABU | ADR7 | 1 | Customizing table ADR7
ICDK900093 | R3TR | TABU | ADR7S2 | 1 | Customizing table ADR7S2
ICDK900093 | R3TR | TABU | ADR8 | 1 | Customizing table ADR8
ICDK900093 | R3TR | TABU | ADR8S2 | 1 | Customizing table ADR8S2
ICDK900093 | R3TR | TABU | ADR9 | 1 | Customizing table ADR9
ICDK900093 | R3TR | TABU | ADR9S2 | 1 | Customizing table ADR9S2
ICDK900093 | R3TR | TABU | ADRC | 1 | Customizing table ADRC
ICDK900093 | R3TR | TABU | ADRCOMCS2 | 1 | Customizing table ADRCOMCS2
ICDK900093 | R3TR | TABU | ADRCS2 | 1 | Customizing table ADRCS2
ICDK900093 | R3TR | TABU | ADRCT | 1 | Customizing table ADRCT
ICDK900093 | R3TR | TABU | ADRCTS2 | 1 | Customizing table ADRCTS2
ICDK900093 | R3TR | TABU | ADRG | 1 | Customizing table ADRG
ICDK900093 | R3TR | TABU | ADRGS2 | 1 | Customizing table ADRGS2
ICDK900093 | R3TR | TABU | ADRT | 1 | Customizing table ADRT
ICDK900093 | R3TR | TABU | ADRTS2 | 1 | Customizing table ADRTS2
ICDK900093 | R3TR | TABU | ADRU | 1 | Customizing table ADRU
ICDK900093 | R3TR | TABU | ADRUS2 | 1 | Customizing table ADRUS2
ICDK900093 | R3TR | TABU | ADRV | 1 | Customizing table ADRV
ICDK900093 | R3TR | TABU | T001 | 1 | Company code core record | #1 Create / Copy Company Code
ICDK900093 | R3TR | TABU | T001Z | 1 | Customizing table T001Z
ICDK900093 | R3TR | TABU | T882 | 1 | Consolidation unit | #55 Consolidation unit
ICDK900093 | R3TR | TABU | TNAPR | 2 | Customizing table TNAPR
ICDK900982 | R3TR | TABU | ADR10 | 1 | Customizing table ADR10
ICDK900982 | R3TR | TABU | ADR10S2 | 1 | Customizing table ADR10S2
ICDK900982 | R3TR | TABU | ADR11 | 1 | Customizing table ADR11
ICDK900982 | R3TR | TABU | ADR11S2 | 1 | Customizing table ADR11S2
ICDK900982 | R3TR | TABU | ADR12 | 1 | Customizing table ADR12
ICDK900982 | R3TR | TABU | ADR12S2 | 1 | Customizing table ADR12S2
ICDK900982 | R3TR | TABU | ADR13 | 1 | Customizing table ADR13
ICDK900982 | R3TR | TABU | ADR13S2 | 1 | Customizing table ADR13S2
ICDK900982 | R3TR | TABU | ADR2 | 1 | Customizing table ADR2
ICDK900982 | R3TR | TABU | ADR2S2 | 1 | Customizing table ADR2S2
ICDK900982 | R3TR | TABU | ADR3 | 1 | Customizing table ADR3
ICDK900982 | R3TR | TABU | ADR3S2 | 1 | Customizing table ADR3S2
ICDK900982 | R3TR | TABU | ADR4 | 1 | Customizing table ADR4
ICDK900982 | R3TR | TABU | ADR4S2 | 1 | Customizing table ADR4S2
ICDK900982 | R3TR | TABU | ADR5 | 1 | Customizing table ADR5
ICDK900982 | R3TR | TABU | ADR5S2 | 1 | Customizing table ADR5S2
ICDK900982 | R3TR | TABU | ADR6 | 1 | Customizing table ADR6
ICDK900982 | R3TR | TABU | ADR6S2 | 1 | Customizing table ADR6S2
ICDK900982 | R3TR | TABU | ADR7 | 1 | Customizing table ADR7
ICDK900982 | R3TR | TABU | ADR7S2 | 1 | Customizing table ADR7S2
ICDK900982 | R3TR | TABU | ADR8 | 1 | Customizing table ADR8
ICDK900982 | R3TR | TABU | ADR8S2 | 1 | Customizing table ADR8S2
ICDK900982 | R3TR | TABU | ADR9 | 1 | Customizing table ADR9
ICDK900982 | R3TR | TABU | ADR9S2 | 1 | Customizing table ADR9S2
ICDK900982 | R3TR | TABU | ADRC | 1 | Customizing table ADRC
ICDK900982 | R3TR | TABU | ADRCOMCS2 | 1 | Customizing table ADRCOMCS2
ICDK900982 | R3TR | TABU | ADRCS2 | 1 | Customizing table ADRCS2
ICDK900982 | R3TR | TABU | ADRCT | 1 | Customizing table ADRCT
ICDK900982 | R3TR | TABU | ADRCTS2 | 1 | Customizing table ADRCTS2
ICDK900982 | R3TR | TABU | ADRG | 1 | Customizing table ADRG
ICDK900982 | R3TR | TABU | ADRGS2 | 1 | Customizing table ADRGS2
ICDK900982 | R3TR | TABU | ADRT | 1 | Customizing table ADRT
ICDK900982 | R3TR | TABU | ADRTS2 | 1 | Customizing table ADRTS2
ICDK900982 | R3TR | TABU | ADRU | 1 | Customizing table ADRU
ICDK900982 | R3TR | TABU | ADRUS2 | 1 | Customizing table ADRUS2
ICDK900982 | R3TR | TABU | ADRV | 1 | Customizing table ADRV
ICDK900982 | R3TR | TABU | T001 | 1 | Company code core record | #1 Create / Copy Company Code
ICDK900982 | R3TR | TABU | T001Z | 1 | Customizing table T001Z
ICDK900982 | R3TR | TABU | T042A | 3 | FBZP payment program config | #25 FBZP extras
ICDK900982 | R3TR | TABU | T042E | 3 | FBZP payment program config | #22 Payment methods per country
ICDK900982 | R3TR | TABU | T042I | 6 | FBZP payment program config | #24 Bank determination/ranking
ICDK900982 | R3TR | TABU | T042W | 1 | FBZP payment program config
ICDK900982 | R3TR | TABU | T042Z | 7 | FBZP payment program config
ICDK900982 | R3TR | TABU | T042ZA | 12 | FBZP payment program config
ICDK900982 | R3TR | TABU | T882 | 1 | Consolidation unit | #55 Consolidation unit

## Migrated Institutes
Institute | Status | Note
IBE | Pre-D01 / Migrated | No T001 creation transport found in D01 E071K. Config exists in live tables but the creation trail is in a predecessor SAP system that was migrated.
UBO | Pre-D01 / Migrated | No T001 creation transport found in D01 E071K. Config exists in live tables but the creation trail is in a predecessor SAP system that was migrated.
UIL | Pre-D01 / Migrated | No T001 creation transport found in D01 E071K. Config exists in live tables but the creation trail is in a predecessor SAP system that was migrated.
UIS | Pre-D01 / Migrated | No T001 creation transport found in D01 E071K. Config exists in live tables but the creation trail is in a predecessor SAP system that was migrated.