SAP CORE REDESIGN PROGRAMME

Programme Management Framework — Milestones, Deliverables & Action Plan

UNESCORE 3.0 | Corporate IT Applications & Digital Transformation

Version 1.0 — April 2026

# 1. Executive Summary & Programme Rationale

This document translates the approved SAP Core Redesign roadmap into a concrete Programme Management Framework. It provides the milestones, deliverables, RACI responsibilities, and risk controls needed to execute the three-pillar redesign as a structured programme under CITO oversight.

## The Three Pillars of SAP Redesign

Pillar 1 — Funds Management (FM) Re-normalisation

SAP FM is currently used mainly for RP with a one-to-one coupling between projects and budget codes. This prevents flexible multi-fund structures and proper budget management. FM must be re-configured to cover all four sources of funds (RP, MCA, OPF, VC) with decoupled fund/project relationships and proper budget availability controls.

Pillar 2 — Project System / WBS Level 4 Implementation

PS/WBS is currently used inconsistently: mainly for VC, with multi-usage of fields and no Level 4 structure. The redesign imposes a standardised Level 4 WBS (thematic/geographic area down to activity-level for Output and Expenses), decoupled from source of funds, with proper SAP controls and full synchronisation with UNESCORE Core Manager.

Pillar 3 — Business Partners (BP) Redesign / Grants Management Implementation

The current Business Partner module lacks proper classification. Vendors, customers, donors, member states and meeting participants are not differentiated with appropriate typologies. The Grants Management (GM) module is non-existent. This pillar redesigns BP typologies and lays the foundation for GM implementation, enabling automated donor management and invoicing.

## Approach

Rather than a big-bang implementation, the programme follows a phased, evidence-based approach:

- 2026 — Design & Validation: Impact analysis, sandbox data mapping, Go/No-Go gate at year-end

- 2027 — Implementation: Data harmonisation, full configuration, UAT, production deployment (FM & PS) aligned with 44 C/5 preparation

- 2027 - 2028 — Business Partners & Grants Management: BP redesign deployment, GM sandbox and go-live

# 2. Programme Milestones

The table below defines 18 key milestones across the three phases. Each milestone has a named primary deliverable, designated owner group, and a target quarter. Focal points from each owner group is to be defined. Milestones are grouped by phase and colour-coded accordingly.

| ID | Milestone | Key Deliverable | Owner | Timeline |
| --- | --- | --- | --- | --- |
| M1 | Programme Governance Setup | Programme Charter, SAP Senior Management Committee TOR, RACI matrix, risk register | CITO / PMO | Q2 2026 |
| M2 | FM Impact Analysis Completed | FM Gap Analysis Report: as-is vs to-be for RP, MCA, OPF, VC funds | DBS (SAP) + FIN + DBM | Q3 2026 |
| M3 | FM Sandbox Data Mapping | Sandbox environment configured; fund structures mapped for all 4 sources. Signed-off by business. | DBS (SAP) + FIN + DBM | Q4 2026 |
| M4 | PS/WBS Impact Analysis Completed | WBS Re-modelling Report: level 4 structure defined, decoupling validated | DBS (SAP) + FIN + DBM + BSP | Q3 2026 |
| M5 | PS/WBS Data Mapping | Sandbox environment configured; project structures mapped for all funds and various complexity (thematic/geographic). Signed-off by business. | DBS (SAP) + FIN + DBM + BSP | Q4 2026 |
| M6 | Business Partners Impact Analysis (Donor) | BP Typology Design Document: donors, customers, vendors, members | DBS (SAP) + FIN + DBM + BSP | Q4 2026 |
| M7 | 2026 Design Phase Review (Go/No-Go) | Design Review Report; updated roadmap; C/5 alignment confirmation | Steering Committee | Q4 2026 |
| M8 | FM Data Harmonisation & Configuration | FM configured in Dev/QA; fund lifecycle rules documented; test results | DBS (SAP) + FIN + DBM | Q2 2027 |
| M9 | PS/WBS Configuration & Testing | WBS structures deployed in Dev/QA; sample mappings for all fund types | DBS (SAP) + FIN + DBM | Q2 2027 |
| M10 | Core Manager Integration Validated | Integration test report: UNESCORE Core Manager <> SAP FM/PS sync | DBS (EPM) + DBS (SAP) | Q3 2027 |
| M11 | User Acceptance Testing (UAT) - FM & PS | UAT sign-off by Finance & Programme business owners | FIN + DBM + DBS | Q3 2027 |
| M12 | FM & PS Production Deployment | Go-live: FM re-normalised, PS Level 4 WBS live; cutover plan executed | DBS (SAP) + CITO/PMO | Q4 2027 |
| M13 | Post-Go-Live Stabilisation | Hypercare report; issue log; updated SOPs and training materials | DBS (SAP) + FIN | Q1 2028 |
| M14 | Business Partners Sandbox Mapping | BP data model in sandbox; classification rules tested across entities | DBS (SAP) + FIN + BSP + DBM | Q3 2027 |
| M15 | Grants Management business process design (with FM & PS changes) | End-to-end business process for Grants Management in SAP with Business Partner typologies, FM & PS changes including upstream Core Manager workflows | DBS (SAP) + DBS (EPM) + FIN + DBM + BSP | Q4 2027 |
| M16 | 2027 Grants Management Design Phase Review (Go/No-Go) | Design Review Report; updated roadmap; C/5 alignment confirmation | Steering Committee | Q4 2027 |
| M17 | Grants Management Configuration | GM configured in sandbox; donor agreement linkage tested end-to-end | DBS (SAP) + FIN + BSP + DBM | S1 2028 |
| M18 | 44 C/5 Readiness Deployment | Full production deployment; 44 C/5 budget cycle supported end-to-end | DBS (SAP) + DBS (EPM) + CITO/PMO + BSP + DBM + FIN | S2 2028 |

Note: M7 and M16 (Design Phase Review are formal Go/No-Go gates. Progression to 2027 and 2028 implementation requires Steering Committee approval based on the design findings.

# 3. Deliverables — Definition & Required Content

This section defines what each key deliverable must contain. Deliverables serve as auditable proof of work and must meet the content criteria below to be accepted by the Steering Committee. SAP Steering Committee is composed of Senior Leadership from DBS, FIN, DBM and BSP. Sponsors must formally sign off each deliverable before the next milestone is triggered.

## Governance Deliverables

Deliverables 1–4 must be completed in Q1 2026 before technical workstreams begin. They establish the governance backbone of the programme.

| Deliverable | Content / What it must include | Producer | Approver |
| --- | --- | --- | --- |
| Programme Charter | Scope statement; objectives; 3 pillars definition; success criteria; governance structure; budget envelope; link to UNESCORE 3.0 | CITO / PMO | CITO + Sponsors |
| RACI Matrix | All roles: Steering Committee, CITO/PMO, DBS SAP team, DBS EPM team, FIN, DBM, BSP, Programme Officers | PMO | Steering Cmt |
| Risk & Issue Register | Risks per pillar (FM/PS/GM); probability x impact; owner; mitigation action; | PMO + Workstream Leads | Steering Cmt |
| Steering Committee TOR | Meeting frequency (monthly recommended); escalation path; decision rights; reporting format | CITO / PMO | Steering Cmt |
| FM Gap Analysis Report & Design | As-is FM configuration per fund (RP, MCA, OPF, VC); one-to-one coupling issues documented; to-be model with decoupled fund/project for all sources of funds; impact on budget controls; Core Manager dependencies | DBS (SAP) + FIN + DBM | Steering Cmt |
| WBS Re-Modelling Report & Design | Current WBS inconsistencies documented; proposed Level 4 structure (thematic/geographic + activity level); to-be model and process; SAP control rules; alignment with Core Manager sync logic | DBS (SAP) + FIN + DBM | Steering Cmt |
| FM Sandbox Mapping Document | Sample fund structures for each source in sandbox; before/after screenshots; mapping rules; data quality issues flagged; Core Manager alignment | DBS (SAP) | DBM + FIN |
| WBS Sample Mapping Document | New RP, MCA, OPF and VC project samples in sandbox; entry creation rules; level 4 activity examples with Output and expense mapping | DBS (SAP) | DBM + FIN + BSP |
| Business Partner Typology Document | Typology definitions: donor, customer, vendor, member state, meeting participant; migration rules from SAP customer to BP; classification logic; volume estimate (15,000 vendors/year) | DBS (SAP) + FIN + DBM + BSP | Steering Cmt |
| Phase 1 Design Review Report | Summary findings per pillar; Go/No-Go recommendation; residual risks; updated timeline; resource needs for 2027; presented to Steering Committee | CITO / PMO | Steering Cmt |
| FM Configuration Document | Detailed technical specs for FM re-configuration; fund types, budget profiles, availability controls; validated in Dev; approved for QA promotion | DBS (SAP) | DBM + FIN + BSP |
| PS/WBS Configuration Document | WBS data model configuration; field usage rules; SAP control settings; consistency checks; Dev environment validated | DBS (SAP) | DBM + FIN + BSP |
| Integration Test Report (Core Manager) | Test cases covering FM <> Core Manager sync; PS <> Core Manager WBS sync; budget availability propagation; error handling; UAT readiness confirmation | DBS (SAP) + DBS (EPM) | DBM + FIN + BSP |
| UAT Plan & Sign-off Document | Test scenarios by business process (carry forward, BOR, fund allocation, project creation, expense reporting); UAT participants; pass/fail criteria; signed acceptance | FIN + DBM + BSP | Steering Committee |
| Training Materials | Role-based guides: Finance & Budget users, Programme Officers; updated SOPs | DBS | DBM + FIN + BSP |
| Cutover & Migration Plan | Data migration approach; cutover sequence; rollback plan; communication & memos; go-live checklist; hypercare period definition | DBS DBM + FIN + BSP (memos) | Steering Cmt |
| Post Go-Live Hypercare Report | Issues logged in first 4-8 weeks; resolution status; system performance; user satisfaction; lessons learned | DBS + DBM + FIN + BSP | Steering Cmt |

# 4. RACI — Roles & Responsibilities

The RACI below covers the core programme activities. Named individuals must be identified by workstream leads and documented in the Programme Charter within Q2 2026.

Key roles:

SAP Steering Committee (programme sponsor & escalation authority)

DBS SAP (technical delivery team — SAP configuration, ABAP, integration)

DBS EPM (Core Manager / UNESCORE integration)

FIN/DBM/BSP (business process owner for funds & projects)

FIN/AFAS / BSP (vendor & partner master data owner)

Project Officers (UAT participants; WBS adoption)

PMO (programme coordination, reporting, risk management)

| Activity / Decision | SAP Steering Committee | DBS SAP | DBS EPM | FIN/DBM/BSP | FIN/FAS & BSP | Project Officers | PMO |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Programme governance & steering | A | I | I | I | I | I | R |
| FM impact analysis & Design | A | R | C | R | - | - | I |
| FM sandbox configuration | I | R | C | C | - | - | I |
| PS/WBS impact analysis & Design | A | R | C | R | - | C | I |
| PS/WBS sandbox mapping | I | R | C | C | - | - | I |
| BP typology design | A | R | C | - | R | - | I |
| Core Manager integration spec | I | C | R | C | - | - | I |
| BP Sandbox mapping | I | R | C | - | C | - | I |
| Grants Management Design | A | R | C | R | R | - | I |
| Grants Management Configuration | I | R | C | C | C | - | I |
| UAT planning & execution | I | C | C | R | R | R | I |
| Training delivery | I | R | R | C | C | I | I |
| Cutover & go-live decision | A | R | R | C | C | I | C |
| Risk management | A | C | C | C | C | I | R |
| Steering Committee reporting | A | C | C | C | C | I | R |

Legend: R = Responsible (does the work)  |  A = Accountable (single sign-off authority)  |  C = Consulted (input required)  |  I = Informed (kept up to date)

# 5. Phased Action Plan

The following action plan details what technical teams and business teams need to do in each phase, enabling clear tracking of who is doing what and when.

## Phase 1 — Design & Impact Analysis (2026)

### Technical Team Actions (DBS SAP + DBS EPM)

- Set up dedicated sandbox environment for redesign testing — isolated from 2026 operational work (Q2 2026)

- Document as-is FM configuration per fund source: fund types, budget profiles, availability controls, posting keys, RP/MCA/OPF/VC coverage gaps (Q2 2026)

- Perform FM impact analysis: model decoupling of project-budget tight coupling; identify transaction-level impacts on active projects (Q3 2026)

- Produce FM sandbox data mapping: configure sample fund structures for all 4 sources with actual data; document mapping rules and data quality gaps (Q4 2026)

- Document as-is WBS inconsistencies: field multi-usage, discrepancies, Core Manager sync, missing Level 4 structure (Q2 2026)

- Perform PS/WBS impact analysis: model Level 4 WBS structure; for all sources of funds; identify SAP control requirements (Q2 2026)

- Produce WBS sample mappings in sandbox: new RP, MCA, OPF, and VC project types at Level 4; validate Core Manager integration at WBS level (Q3 2026)

- Document as-is Customer (Business Partner) configuration; identify typology gaps; draft BP re-classification rules (donor, customer, vendor, member state) (Q4 2026)

- Prepare Design Review Report for Steering Committee Go/No-Go (Q4 2026)

### Business Team Actions (FIN, DBM, BSP)

- Provide named business owners and deputies for each pillar by May 2026 — no analysis can start without a confirmed business counterpart (Q2 2026)

- Co-author FM to-be requirements with DBS SAP: define expected fund lifecycle rules, budget control expectations per fund source, reporting needs (Q3 2026)

- Validate FM sandbox mappings: confirm that proposed fund structures reflect actual/adjusted budget management practices; identify edge cases (Q4 2026)

- Co-author PS/WBS to-be requirements: define Level 4 WBS naming conventions, activity types, Output mapping rules, project specific needs (Q3 2026)

- Identify pilots for WBS sandbox mapping exercises; provide actual project data for sample mapping (Q3 2026)

- Validate WBS sample mappings: confirm Level 4 structure meets programme officer and reporting needs (Q4 2026)

- Provide vendor/customer/donor master data typology breakdown to DBS for BP analysis (Q3 2026)

- Participate in Go/No-Go Steering Committee review; confirm business readiness for 2027 implementation (Q4 2026)

## Phase 2 — Implementation & Deployment (2027)

### Technical Team Actions

- Build FM configuration in Development environment based on Phase 1 design; apply fund lifecycle rules, budget profiles, availability controls (Q2 2027)

- Promote FM configuration to QA; execute technical test scripts; fix defects; document configuration baseline (Q1 2027)

- Build PS/WBS Level 4 configuration in Development; implement consistency controls; configure Core Manager synchronisation points (Q2 2027)

- Execute integration test suite: FM <> Core Manager; PS <> Core Manager WBS sync; end-to-end budget flow from Core Manager to SAP commitment (Q3 2027)

- Support UAT: provide test environment, assist with data setup, log and fix defects raised by business testers (Q3 2027)

- Develop and execute cutover plan: data migration approach, go-live sequence, rollback procedure, cutover communication to all institutes (Q3-Q4 2027)

- Execute production deployment; provide hypercare support for 12 weeks post go-live (Q4 2027)

### Business Team Actions

- Review and sign off FM and PS/WBS configuration documents before QA promotion (Q1-Q2 2027)

- Lead UAT: design business test scenarios covering carry-forward, BOR processing, fund allocation, project creation, expense reporting; execute tests; log and accept/reject results (Q3 2027)

- Provide formal UAT sign-off by named business sponsor before go-live approval (Q3 2027)

- Prepare memos, participate in communication and change management: inform programme officers of new WBS rules; provide feedback on training materials (Q3 2027)

- Train finance and programme teams using DBS-produced training materials; ensure all users complete training before go-live (Q3-Q4 2027)

- Support post go-live stabilisation: monitor daily operations, report issues through agreed channel, participate in hypercare review meetings (Q4 2027)

## Phase 3 — Business Partners & Grants Management (2028)

### Technical Team Actions

- Configure BP typologies in sandbox; test re-classification rules across all entity types; validate migration from SAP customer objects (Q3 2027)

- Configure Grants Management module in sandbox; link to normalised FM and PS structures; test donor agreement lifecycle end-to-end (S1 2028)

- Implement GM <> Core Manager integration for donor data, organisations and VC workflow (S1 2028)

- Execute BP data migration to production; deploy GM (S1 2028)

### Business Team Actions

- Validate BP typology definitions: confirm donor, customer, vendor, member state classification rules are operationally correct (Q4 2026)

- Design and validate Grants Management end-to-end process: from donor agreement in Core Manager to GM posting in SAP; confirm automation meets audit and compliance requirements (Q4 2027)

- Support GM UAT and provide sign-off; confirm 44 C/5 budget cycle processes work end-to-end (S1 2028)

# 6. Programme Risk Register

The following key risks have been identified based on the assessment documents and programme context. The risk register must be reviewed monthly by the PMO and presented at each Steering Committee meeting.

| Risk | Prob. | Impact | Owner | Mitigation |
| --- | --- | --- | --- | --- |
| FM decoupling breaks existing budget controls in active projects | Med | High | DBS SAP + DBM + FIN | Detailed impact analysis in sandbox before any config change; rollback plan per release |
| ABAP/technical capacity insufficient for parallel delivery of 2026 priorities and redesign | High | High | CITO + DBS | Resource plan with explicit capacity allocation; prioritisation protocol agreed with sponsors ; activate external partner support ; budget envelope for external support pre-approved in UNESCORE 3.0; |
| Business owners insufficiently available for design workshops and UAT | Med | High | PMO + Sponsors | Formal time commitment in governance charter; named deputies for each business area |
| WBS re-modelling disrupts Core Manager <> SAP synchronisation | Med | High | DBS SAP + DBS EPM | Joint integration test plan from Day 1; Core Manager team in scope of all PS design sessions |
| Adoption resistance - inconsistent WBS usage across entities | Med | Med | DBS + DBM + BSP + FIN | Change management plan (communications, materials, trainings); mandatory compliance framework post go-live |
| Data quality issues in vendor/customer master data delay BP migration | High | Med | FIN + + BSP + DBS SAP | Data quality assessment as part of Phase 1; cleansing plan before migration; double entry and consolidation rules to be clarified |
| 44 C/5 budget cycle constraints compress deployment window | Med | High | DBS | Timeline anchored to C/5 deadline from outset; no-go criteria defined at M7 review |

Probability and impact are rated Low / Med / High. All High-High risks require an immediate mitigation action plan within 2 weeks of identification.

# 7. Programme Governance & Reporting

## Governance Structure

- SAP Steering Committee:

  - Monthly

  - Chaired by DIR/DBM, DIR/FIN, DIR/DBS, DIR/BSP(?)

  - Members include FIN – DBM - BSP key business counterparts (Amol, Anssi, Lionel, BSP tbd), DBS leads, PMO.

  - Reviews milestone status, risks, and Go/No-Go gates

- Working Groups (per pillar : FM ; PS/WBS ; BP/GM):

  - Weekly or bi-weekly – to be adjusted according to the phase. Design phase recommendation is weekly.

  - DBS lead(s) + business focal point(s)

  - Reviews technical progress, resolves design questions, tracks deliverable completion

- PMO:

  - CITO/PMO

  - Maintains consolidated programme plan, RACI, risk register, and status reporting. Issues monthly programme status report to CITO and Steering Committe

DBS focal points:

PMO: Didem, Francois

DBS Lead: Didem

DBS SAP Lead: Pablo

Pillar FM DBS lead: Illya

Pillar PS/WBS lead: Rodolfo

Pillar BP/GM lead: Rodolfo

DBS ABAP lead: Nicolas

DBS EPM team: Alexandra, Vinicius, Sylvain, Orestis

DBS External Partners

FIN focal points:

Pillar FM:

Pillar PS/WBS:

Pillar BP/GM:

DBM focal points:

Pillar FM:

Pillar PS/WBS:

Pillar BP/GM:

BSP focal points:

Pillar FM:

Pillar PS/WBS:

Pillar BP/GM:

## Reporting

| Report / Meeting | Frequency | Audience | Content |
| --- | --- | --- | --- |
| Steering Committee Status Report / Presentation | Monthly | Steering Committee Members | Milestone RAG status, risks, decisions needed, budget |
| Working Group Minutes | Weekly or Bi-weekly | DBS + Business counterparts | Progress vs plan, blockers, design decisions, action items |
| Deliverable Acceptance Form | Per deliverable | Steering Committee | Formal sign-off confirming deliverable meets acceptance criteria |
| Risk Register Review | Monthly (embedded in SC) | Steering Committee | Updated risk ratings, mitigation status, new risks added |
| Go/No-Go Review (M7, M11, M16, M18) | At gate milestones | Steering Committee | Phase outcomes, readiness assessment, formal decision and sign-off |

## Deliverable Quality Gates

All deliverables must pass a two-stage quality check before acceptance:

- Technical review: DBS SAP lead confirms technical correctness and completeness against the acceptance criteria defined in Section 3.

- Business review: Named business owner confirms the deliverable reflects actual business requirements and is fit for the next phase.

No milestone is marked complete until both reviews are signed off. The PMO maintains the Deliverable Tracker as the authoritative record.

## Documentation & Methodology

Teams: Channel for communication and programme deliverables

Confluence: Design and technical documents (reference repository)

JIRA: 2-3 weeks Sprint planning, user stories, UAT and post go-live follow-up

# 8. Immediate Next Steps — Q2 2026

The following actions must be completed within 30 days to mobilise the programme:

| # | Action | Owner | Due |
| --- | --- | --- | --- |
| 1 | Formally appoint Programme Manager / PMO resource | CITO | Week 2 |
| 2 | Draft and circulate Programme Charter for Steering Committee approval | PMO + CITO | Week 4 |
| 3 | Convene May Steering Committee meeting; agree governance TOR | CITO | Week 4 |
| 4 | Confirm named business owners for each pillar (FM: FIN/DBM, PS: FIN/DBM/BSP, BP: FIN/FAS, BSP) | Business counterparts (Amol, Anssi, Lionel, BSP) | Week 3 |
| 5 | Confirm DBS SAP team capacity allocation for 2026 redesign workstream (vs operational backlog) | DBS Lead + CITO | Week 3 |
| 6 | Set up dedicated sandbox environment for redesign (separate from operational development) | DBS SAP | Week 6 |
| 7 | Kick off FM impact analysis (M2) — schedule working sessions with FIN/DBM | DBS SAP + FIN/ + DBM | Week 5 |
| 8 | Complete RACI with named individuals across all roles | PMO | Week 4 |
| 9 | Establish programme SharePoint / repository for all deliverables: Set-up Confluence for design documents; Set-up JIRA for implementation and testing | PMO | Week 3 |

Document Control

| Version | 1.0 | Date | April 2026 |
| --- | --- | --- | --- |
| Prepared by | CITO / PMO Office | Status | For Steering Committee Review |
| Classification | Internal — Restricted | Next Review | Q2 2026 Steering Committee |